Sr. No……….

BID DOCUMENT

Tender For Optical Fiber Cable

Construction Works

TENDER NO:-GMTD/SOL/Tender/OFC/2014-15/02. Dated :- 24-02-2015.

ROUTE: -

SECTION: -

O/o GENERAL MANAGER TELECOM DISTRICT

SOLAN (HP)

Cost of Tender Document: -				As per NIT

SALE OF TENDER DOCUMENT                                FROM  11-03-2015 to 07-04-2015 ON ALL   WORKING DAYS BETWEEN 10:00HRS TO 13.00 HRS,

LAST DATE OF SUBMISSION OF

TENDER DOCUMENTS	UP TO 15.00 HRS. on or before 07-04-2015 in the Tender box kept in the office of the AGM (NWP), O/o GMTD SOLAN (HP)

DATE OF OPENING OF bid                       		15.30 HRS. ON   07-04-2015.

ISSUED TO …………………………………………………………………………………….

………………………………………………………………………………………

……………………………………………………………………………………….

……………………………………………………………………………………….

No. /D.D. No……. ……………………………………….dated……………………………….

DATE OF ISSUE: … /….. /…………

AGM (NWP)

O/o GMTD Solan (HP)

TABLE OF CONTENTS

Section 	  Content 						              	Page No.

### QUALIFYING BID DOCUMENT

- Notice  Inviting Tender		3-5

- Bid Form 		6

- Bidder’s Profile		7-8

- Instruction  to Bidders		 9-17

- General (commercial) conditions of The contract		18-34

- Special conditions of the contract 		35-44

- Participation of near relatives of the BSNL Employee		45

- Scope of work and jurisdiction of Contract 		46-47

- OF Cable construction Specifications   		48-73

- Agreement 		74-75

- Letter of authorization for attending 		 76

- List of the documents to be submitted along with bid		 77

- Rate of Empty Cable drums					 78

- Appendix								 79-87

FINANCIAL BID (cover page)	                                                                         88

XV.   Financial Bid		 89-94

XVI.  Certificate by Bidder in case of download.		 95.

SECTION – I

BHARAT SANCHAR NIGAM LIMITED

OFFICE OF GENERAL MANAGER TELECOM DISTRICT SOLAN – 173211 (H.P.)

# NOTICE INVITING TENDER

# TENDER FOR OPTICAL FIBER CABLE CONSTRUCTION WORK

NIT NO: - GMTD/SOL/Tender/OFC/2014-15/07. 				Dated :- 24-02-2015.

Properly sealed Tenders (Sealed by Packing PVC tape/Conventional Sealing Wax) are invited by the General Manager Telecom District Solan for and on behalf of B.S.N.L. from the eligible contractors up to 1500 hours of 07-04-2015 for UNDERGROUND OPTICAL FIBER CABLE CONSTRUCTION WORKS. For details, please visit our Web site: - www.hp.bsnl.co.in.

- sd -

AGM (NWP)

O/o GMTD Solan-173211 HP

BHARAT SANCHAR NIGAM LIMITED

O/oGENERAL MANAGER TELECOM DISTRICT SOLAN – 173211 HP

NOTICE INVITING TENDER

# TENDER FOR OPTICAL FIBRE CABLE CONSTRUCTION WORK

NIT NO: - GMTD/SOL/Tender/OFC/2014-15/02         				  Dated 24-02-2015

Properly sealed Tenders (Sealed by Packing PVC tape/Conventional Sealing Wax) are invited by the General Manager Telecom District Solan for and on behalf of BSNL from the eligible contractors registered with EPF registration authorities for the following works:-

1.  Name of work:-UNDERGROUND OPTICAL FIBRE CABLE CONSTRUCTION WORK

2.  Area of contract & Eligible Contractors:-

| A) OFC Route/ Section |
| --- |
| S. No. | Name of Route | Route Length in Km. | Estimated Cost (Rs.) | Tender Document Cost | EMD (Rs.) |
| Section (A) New route under DE(O/D) Parwanoo |
| A-1) | Nanakpura-Kalujhinda under Baddi Sub-div. | 3.1 |  |  |  |
|  | Total RKM | 3.1 | 9,30,000/- | Rs. 500 + 69(VAT)= 569/- | 23250/- |
| Section (B) OFC routes for GSM /WLL BTS under DE(O/D) Solan |
| B-1) | BTS Himani Hotel –Joint on Mall Road Solan | 0.5 |  |  |  |
| B-2) | BTS Sunny side - Joint near DC office Solan | 1.0 |  |  |  |
| B-3) | BTS Civil Hospital -Joint near Kotla Nala Solan | 1.0 |  |  |  |
| B-4) | BTS Kailer -Joint near Kailar on Subathu Road | 3.0 |  |  |  |
| B-5) | BTS Barog- Joint near T/E Barog | 1.0 |  |  |  |
| B-6) | BTS Basal – Joint on Dharot Road Solan | 1.0 |  |  |  |
| B-7) | BTS Dhobighat- Joint on Rajgarh Road Solan | 1.0 |  |  |  |
| Total RKM | 8.5 | 25,50,000/- | Rs. 1000+ 138(VAT)= 1138/- | 63,750/- |

3.	Experience:-  Experience of having successfully completed similar works during last seven years ending last day of month previous to the one in which application are invited should be either of the following :-

(a) Three similar completed works costing not less than the amount equal to 40% of the estimated cost

OR

(b) Two similar completed works costing not less than the amount equal to 50% of the estimated cost.

OR

(c)  One similar completed work costing not less than the amount equal to 80% of the estimated cost

4.	Period of Contract: - One Year from the date of agreement or completion of work or acceptance of fresh Tender whichever is earlier. However GMTD Solan reserves the right to increase or decrease the quantum of work by 25% & also to extend the time period of contract for further 90 days on the same terms & conditions in the interest of BSNL.

5.	Mode of Payment for obtaining theTender Document containing detailed description of works and Terms & Conditions can be purchased from :-AGM (NWP) O/o GMTD Solan – 173211 HP by paying cost of  Bid Document (Non-refundable) in cash or in the shape of Demand Draft drawn in favour of AO (Cash), O/o GMTD Solan (Payable at Solan). Complete Tender document (Bid Document and Technical Specification Document can also be downloaded from by selecting “SSA”, then “Solan”, from the “Tenders” link of website – www.hp.bsnl.co.in . The cost of bid document should be attached in the form of DD drawn on or before 06-04-2015 in favor of AO (Cash), O/o GMTD Solan payable at Solan. Bidders should check the completeness of downloaded document. Any discrepancy found if any from the original bid document in any form at any stage, will lead to rejection of Tender. Bid Security has to be paid in the form of Demand Draft issued by a scheduled bank drawn in favour of Accounts Officer (Cash), O/o GMTD Solan, payable at Solan.

6. 	Separate Tender form must be filled for each  section (One Tender form shall be valid for all routes under one section’s work only).

7.	Sale of Tender Document: -   From AGM (NWP) O/o GMTD Solan HP between 10.00 Hrs to 13.00 Hrs from 11-03-2015 to 07-04-2015 on all working days.

8.	Time and Last date of submission of Bids: - Up to 1500 Hours of 07-04-2015 in the 	Tender box kept in the chamber of AGM (NWP) O/o GMTD Solan.

9.	Time of opening of Bids: -   At 1530 Hours on 07-04-2015 in O/o GMTD Solan in the chamber of AGM (NWP) O/o GMTD Solan.

10.   	The Tender which is not accompanied by the requisite Bid Security, shall be summarily rejected. Tender will not be accepted / received after expiry date and time.

11.   	GMTD Solan reserves the right to accept or reject any / all the bids with out assigning any reason there of and with out incurring any liability to the affected bidder (s) on account of this action.

AGM (NWP)

O/o GMTD Solan (HP)

SECTION - II

BID FORM

Tender No __________________________________Date:___/________/ ______

To

The General Manager Telecom District

BSNL, Solan (H.P.)

PIN-173211.

Dear Sir,

Having examined the conditions of contract and specifications including NIT No ……………… ………………. the receipt of which is hereby duly acknowledged , we, undersigned, offer to execute the work of Optical Fibre Cable construction work ……………………………………... in conformity with said drawings, conditions of contract and specification as may be ascertained in accordance with the attached herewith and  made part of this Bid.

We undertake, if our Bid is accepted, we will execute the work in accordance with specifications, time limits & terms and conditions stipulated in the Tender document.

If out Bid is accepted, we shall submit the securities as per the conditions mentioned in the contract.

We agree to abide by this Bid for a period of 180 days from the date fixed for Bid opening and it shall remain binding upon us and may be accepted at any time before the expiry of that period.

Until a formal Agreement is prepared and executed, this Bid together with your written acceptance thereof in your notification of award shall constitute a binding contract between us.

Bid submitted by us is properly sealed and prepared so as to prevent any subsequent alteration and replacement.

Dated………………………..

Signature of Authorized Signatory……………….

In capacity of……………………………………..

Duly authorized to sign the bid for and on behalf of ……………

Witness………………

Address………………

Signature……………

Signature of Bidder

SECTION – III

BIDDER’S PROFILE

General:

- Name of the bidder /firm ___________________________________

- Name of the person submitting  the Tender whose Photograph is afixed

Shri / Smt. ________________________________________________

(In case of Proprietary / Partnership firms, the Tender has to be signed by Proprietor /

Partner only, as the case may be)

- Address of the firm

…………………………………………………………………………………………

…………………………………………………………………………………………

- Telegraphic Address ……………………………………………………………………….

- Tel. no. (with STD code )

(o) …………. (Fax)………………… (R)…………………..…

- Registration & incorporation Particulars of the firm:

  - Proprietorship

  - Partnership

  - Private Limited

  - Public Limited

(Please attach attested copies of documents of registration / incorporation of your firm with the competent authority as required by business law)

7. Name of Proprietor/Partners /Directors……………………………………...........

……………………………………………………………………………………..

8. Bidder’s Experience………………………………………………………………

…………………………………………………………………………………………

9. Bidder’s bank, its address and his current account number ……………...............

………………………………………………………………………………….……

10. Permanent Income Tax number, income Tax circle ………………………………

…………………………………………………………………………………………

(Please attach a copy of last/latest income tax return)

- Infrastructural capabilities:

  - Capacity of trenching per day (in meters)……………………………………….

  - Capacity of cable laying per day (in meters)……………..…………………….

  - Capacity of pulling cable through duct per day (in meters)……………………..

  - Capacity of engaging mazdoors per day…………………………………………

  - Particulars of vehicles available with the Tenderer:

Type of Vehicle(s)	Registration number

  - Particulars of other machines possessed by the contractor which can help in trenching, cable laying and cable Pulling ;

…………………………………………………………………………………………………………………………………………………………………………………

- Details of Technical and supervisory Staff:

- EPF Registration No :-

I / We hereby declare that the information furnished above is true and correct.

Place:

Date:

Signature of bidder /Authorized signatory…………………………

Name of the bidder ………………………………………………

Seal of the bidder

SECTION - IV

Instruction to Bidders

INTRODUCTION:

1.     DEFINITIONS

- Bharat Sanchar Nigam Limited: The Bharat Sanchar Nigam Limited means the Bharat Sanchar Nigam Limited and its Board of Directors.

- BSNL: The BSNL means the Bharat Sanchar Nigam Limited under the Ministry of Communications, which invites the Bids on behalf of the Bharat Sanchar Nigam Limited. All references of:

BSNL

Chief General Manager Telecom

General Manager Telecom

Deputy General Managers Telecom

Assistant General Manager Telecom

Sub Divisional Engineer

Junior Telecom Officer

Accounts Officer

Chief Accounts Officer

Junior Accounts Officer

Including other officers in the BSNL, whatever designations assigned to them from time to time, who may be the In-charge of direction, supervision, testing, acceptance and maintenance including their successor(s) in the office appearing in various clauses shall be taken to mean the Bharat Sanchar Nigam Limited under the Ministry of Communications, Govt. of India.

- The GMTD Solan means the head of Solan SSA and his successors.

- The jurisdiction of the GMTD Solan: The jurisdiction of GMTD Solan means the Area which coincides area of SSA Solan.

e)     Representative of The GMTD Solan:  Representative of GMTD Solan means officer and  staff for the time being in “Solan SSA” deputed by the GMTD Solan for inspection or supervising the work or testing etc.

f)    Engineer-in–charge:   The Engineer –in –charge means the Engineering Officer nominated by the BSNL to supervise the work, under the contract (Minimum Divisional Engineer level officer).

g)    Site Engineer:   Site Engineer Shall mean an SDE of the BSNL who may be placed by the GMTD Solan as in charge of the work at site at any particular period of time

h)    A/T Unit:   A/T Unit shall be mean Acceptance and testing unit of the BSNL.

i)          A/T Officer: An officer authorized by GMTD Solan /T&D Circle to conduct A /T.

j)	Contract: The term contract means the documents forming the Tender and acceptance  there of and the formal agreement executed between the competent authority on behalf of the President of India and the contractor, together with the documents referred to therein inducing these conditions  the specifications , designs, drawings and instruction issued from time to time, by the engineer in charge and all these documents taken together shall be deemed to form one contract and shall be complementary to one another , In the contract, the following expressions shall, unless the context otherwise requires ,  have the meanings, hereby respectively assigned to them, The expression works or work shall unless there be something either in the subject or context repugnant to such construction , to be executed whether temporary or permanent, and whether original, altered, substituted or additional.

k)	Contractor: The contractor shall mean the individual, firm or company, enlisted with Department of Telecom/BSNL in accordance with procedure for enlistment of contractor, whether incorporated or not, undertaking the works and shall include the legal personal representative of such individual or the persons composing such firm or company, or the successors of such firm or company, or the successors of such firm or company and the permitted assignees of such individual, firm or company.

l)       Work: The expression “work” shall unless these be something either in the subject or context  repugnant to  such construction be construction be construct and taken to  mean the works by or by virtue of the contract contracted to  be executed whether temporary or permanent and whether original altered, substituted or additional.

m)	Schedule(s): Schedule(s) referred to in these conditions shall mean the relevant schedule(s) or the standard schedule of rates mentioned in the document.

n)	Site: The site shall mean the land / or other places on, into or through which work is to be executed under the contract or any adjacent land, path or street through which, the work is to be executed under the contract or any adjacent land, path or street which may be allotted or used for the purpose of carrying out the contract.

o)	Normal time or stipulated time: Normal time or stipulated time means time specified in the work order to complete the work.

p)	Extension of Time: Extension of time means the time granted by the BSNL to complete the work beyond the normal time or stipulated time.

q)   	 Date of Commencement of work: Date of commencement of work means the date of   actual commencement of work or 7th day from the date of issue of work order, whichever is earlier.

r)	Due date of completion: Due date of completion shall be the date by which the work shall be completed/executed at site including clearance of site.

- Duration of completion of work: The duration of completion of work or completion time shall be time specified in the work order plus extension of time granted, if any.

- Excepted risk: Excepted risk are due to war (whether declared or not ), invasion , act of  foreign enemies, hostilities, civil war, rebellion, revolution, insurrection, military or usurped power, any acts of Government damages from aircraft, acts of God, such as earthquake, lightening, fire, epidemic and unprecedented floods and  other causes over which , the contractor has no control  and the same having been accepted as such , by the Accepting Authority or causes solely due to use or occupation by the government of the part of the work in respect of which a certificate of completion has been issued.

- ELIGIBILITY OF BIDDERS:

The invitation of bids is open to all eligible contractors having EPF Registration and as per their eligibility conditions mentioned in NIT of this Tender document.

3.    BID DOCUMENTS:

  - The construction work to be carried out , goods required , bidding procedures and contract terms are prescribed in the Bid Documents , The Bid Document include:

Qualifying Bid:

      - Notice Inviting Tender

      - Bid Form

      - Bidder’s profile

      - Instruction to Bidders

      - General (Commercial) conditions of the contract

      - Special conditions of contract

      - Scope of work and jurisdiction of the contract

      - Technical Specifications

3.1.1.9	 	        Agreement

3.1.1.10                    Letter of authorization for attending bid opening

3.1.1.11                    Rates of empty cable drums (Section XII)

3.1.1.12	        Certificate from bidders.

3.1.1.13	        Material security Bond form.

3.1.2        Financial bid

3.1.2.1     Section XIV to be considered and filled up.

3.2	The Bidder is expected to examine all instructions, forms, terms and specifications in the bid documents. Failure to furnish all information required as per the bid Documents or submission of bids not substantially responsive to the bid Documents in every respect will be at the bidder’s risk and shall result in rejection of the bid.

4	QUERRIES ON BID DOCUMENTS:

A prospective bidder, requiring any clarification of the Bid Documents shall notify the BSNL in writing or by fax or cable at the BSNL’s mailing address indicated in the invitation for bids The BSNL shall respond in  writing to any request for clarification of the bid Documents , which it receives not later than 7 days prior to the date for the opening of the bids, Copies of the query (without identifying the source) and the clarification  by the BSNL shall be sent to all the prospective bidders who have purchased the bid documents and all such clarifications issued by the BSNL will form part of the bid document .

5.	AMENDMENT OF BID DOCUMENTS:

5.1   At any time, prior to the date for submission of bids, the BSNL may, for

any reason whether sue motto or in response to a clarification requested by a

prospective bidder, modify the bid documents by amendments.

  - The amendments shall be notified in writing or by telex or FAX to all prospective bidders on the address intimated at the time of purchase of bid document from the BSNL and these amendments will be binding on them.

  - In order to afford prospective bidders reasonable time to take the amendments into account in preparing their bids, the department may, at its discretion , extend the deadline for the submission /opening of bids suitably.

C.	PREPARATION OF BIDS

6.	Cost of Bidding:

The bidder shall bear all costs associated with the preparation and submission of the bid. The BSNL, will in no case, be responsible or liable for these costs, regardless of the conduct or outcome of the bidding process.

- DOCUMENTS ESTABLISHING BIDDER’S ELIGIBILITY AND QUALIFICATIONS:

The bidder shall furnish, as part of his bid documents establishing the bidders, eligibility, the following documents:

i.)	Bid security in accordance to clause no. 8

ii) 	Tender document, in original, (Page 1 to page 143) duly filled in and signed by Tenderer or his authorized representative along with seal on each page. All corrections and overwriting must be initialed with date by the Tenderer or his authorized representative.

iii)	The copy (duly attested by a Gazetted officer) of experience certificate issued by an officer not below the rank of Divisional Engineer.

iv) 	The registration of the firm authenticated copy of partnership deed in cases of partnership firm.

v)	Bid Form, duly filled in, as per section II.

vi)       	Tenderer’s profile duly filled in, as per section III of the Tender document.

vii)   	Original “Power of Attorney” in case person other than the Tenderer has signed the Tender documents.

viii)   	List of qualified experienced personnel, having detail as name and address, who are working for the Tenderer, who will be deployed for the work.

ix)	PAN Number attested copy.

- EPF Registration.

- Copy of the Service Tax Registration number.

- BID SECURITY:

  - The bidder shall furnish, as part of his bid, a bid security (EMD) for an amount as mentioned in NIT. No interest shall be paid by the BSNL on the bid security for any period, whatsoever.

  - The bid security is required to protect the BSNL against the risk of bidders conduct, which would warrant the security’s forfeiture, pursuant to para 8.7.

  - Bid security shall be paid in the form of crossed demand draft issued by a scheduled bank, drawn in favour of Accounts Officer (Cash) % GMTD Solan payable at Solan.

  - A bid not secured in accordance with para 8.1 & 8.3 shall be rejected by the BSNL as non-responsive.

  - The bid security of the unsuccessful bidder will be refunded as promptly as possible.

  - The successful bidders bid security will compulsorily be converted into part performance security in accordance with clause 25.

  - The bid security shall be forfeited: -

    - If a bidder withdraws his bid during the period of bid validity specified in the bid document or

    - If the bidder makes any modifications in the terms and conditions of the Tender before acceptance of the Tender, which are not acceptable to the BSNL or

    - If the documents submitted by bidders are found to be false/forged at any stage. or

    - In case of successful bidder, if the bidder fails:

i) To sign the agreement in accordance with clause 25

ii) To furnish performance security in accordance with clause 24.

- BID PRICES:

  - The bidder shall give the total composite price inclusive of all levies and taxes, packing, forwarding, freight and insurance in case of materials to be supplied and inclusive of all taxes (excluding Service Tax) and levies in case of works to be executed. The contractor shall be responsible for transporting the materials, to be supplied by the BSNL (at the SSA store) or otherwise to execute the work under the contract, to site at his /their own cost. The offer shall be in the form Indian Rupee.

  - Prices shall be quoted by the bidder in Financial bid (Section XIV) in Figures and in Words in case of any disparity in amount in Figures and Words the amount quoted in Words will be taken as final. Prices quoted at any other place shall not be considered.

  - The price quoted by the bidder shall remain fixed during the entire period of contract and shall not be subject to variation on any account. A bid submitted with an adjustable price quotation will be treated as non-responsive and rejected.

  - Discount, if any, offered by the bidders shall not be considered unless they specifically indicated in the financial bid. Bidders desiring to offer discount shall therefore modify their offers suitably while quoting and shall quote clearly net price taking all such factors like Discount, free supply, etc. into account.

  - Service Tax, if applicable, will be shown separately in the bill and shall be paid by BSNL and will be deposited to Excise Department by the contractor and the challans must be produced in next month to BSNL.

- PERIOD OF VALIDITY OF BIDS:

  - Bid shall remain valid for 180 days from date of opening of the bid. THE BSNL SHALL REJECT A BID VALID FOR A SHORTER PERIOD AS NON-RESPONSIVE.

  - The BSNL reserves the right to request the lowest 2 bidders as per read out line on the opening day to extend the bid validity for a period of further 120 days and the bidder has to necessarily extend the bid validity. Refusal to extend the bid validity will result in forfeiture of the bid security. A bidder accepting the request and extending the bid validity will not be permitted to modify his bid.

11.       SIGNING OF BID:

  - The bidder shall submit, as a part of his bid, the bid documents (in original) duly signed on each and every page, establishing the conformity of his bid to the bid documents of all the works to be executed by the bidder under the contract.

(Note: The bidder is advised to keep a photocopy (at his own cost) of the bid documents for his own reference)

  - The  bid shall contain no inter-lineation, erasures or overwriting except as necessary to correct errors made by the bidder in which case such corrections shall be signed with date by the person or persons signing the bid.

12        SUBMISSION OF BIDS

12.1	Method of preparation of bid:

Bid for each Tender should be submitted in two envelopes placed inside a main cover envelope. These envelopes should contain the following;

| Envelope | Marked on the cover | Contents of Envelope |
| --- | --- | --- |
| First | Qualifying Bid | Bid security and containing documents as per clause 7 & 8. |
| Second | Financial Bid | Rates duly quoted by the bidder in the prescribed format (Section XIV ) |

On all these envelopes the name of the firm and whether “Qualifying”  OR “Financial” bid must be clearly mentioned and should be properly sealed (with sealing wax/packing PVC tape). Two envelopes are to be placed inside an outer envelope and properly sealed (with sealing wax/packing PVC tape). The envelope containing cost of Tender document (if downloaded from web site) should be attached on outer envelop.  The Tenders which are not submitted in above mentioned manner shall be rejected summarily.

  - All envelopes (2 inner & one outer ) must bear the following ;

Tender for OF Cable Construction Works

“NOT TO OPEN BEFORE (DUE DATE OF TENDER)”

(Tender no.___________________________)

(Name of Route ____________________________________________)

(Section ___________________________________________)

(Name and Address of Bidder ________________________________)

  - The bidder will be bound by all terms, conditions & specifications as detailed in the   Tender     documents.

  - Any Tender with conditions other than those specified in the Tender document is liable to be summarily rejected. No modification by the contractor in any of the conditions will be permitted after the Tender is opened.

13.	                PROCESS OF SUBMISSION OF BIDS:

13.1	Bids should be dropped in person in the Tender box placed in the office of DE (Plg.) O/o GMTD Solan, before the closing (date &time) of Tender, as mentioned in NIT. The bidder is to ensure the delivery of the bids at the correct address, the BSNL shall not be held responsible for delivery of bid to the wrong address. The slit of the Tender box will be sealed immediately after the specified time for receipt of Tender. Any bid presented in person after the sealing of box will not be received by GMTD SOLAN or by any of the subordinates or will not be allowed to be deposited in the Tender box.

  - Postponement of Tender opening: Whenever it is considered necessary to postpone the opening date of Tenders, quick decision must be taken and communicated to the Tenderers who have purchased the Tender documents and shall be at least one day before the original date of opening. The reasons for postponing the Tender shall be recorded in writing. Such notice of extension of date of opening shall also be put- up on the notice board and also published in the newspapers in which original NITs have been published. If the date of opening of bids is declared as holiday, the bids will be opened on the next working date at the same time and venue.

13.3	The BSNL if subsequently declares the date fixed for opening of bids as holiday, the revised schedule will be notified. However, in absence of such notification, the bids will be opened on next working day, time and venue remaining unaltered.

14.	LATE BIDS:

  - Tenders will not be received after the specified time of closing of the Tender and the same shall be rejected and returned unopened to the bidder. It is the sole responsibility of the Tender that he should ensure timely submission of Tender.

- MODIFICATIONS AND WITHDRAWL OF BIDS :

  - The bidder may modify or withdraw his bid after submission and before opening, Provided that the intimation is deposited by the bidder in a properly sealed envelope (With Wax/packing PVC tape) in  the Tender box, before the scheduled time & date  for closing  of Tender    .

  - No bid shall be modified subsequent to the deadline for submission of bids.

BID OPENING AND EVALUATION:

16	      Opening of Bids by the BSNL:

16.1          The BSNL shall  open the bid  in  the  presence  of bidders or his authorized representatives  who choose to attend at 1500 Hrs. on due date. The bidder’s representative who are present, shall sign an attendance register, The bidder shall submit authority letter to this effect before they are allowed to participate in the bid opening (A format is given in section –X).

16.2	A maximum of one (1) representative for any bidder shall be authorized and permitted   to   attend the bid opening.

16.3           The bids shall be opened in the following manner:

16.3.1	The bid opening committee shall count the number of bids and assign serial numbers to  the bids, For example, if 10 Tenders have been received in the bids that shall be numbered as 1 of 10, 2 of 10 etc. The entire member shall initial on the outer envelopes of all the bids with date.

16.3.2	The envelopes containing the Tender offer and not properly sealed, as required vide Para   16.3.1 shall not be opened and shall be rejected out rightly. Sealing the cover by gum will not be treated as sealed cover. The reason for not opening such Tender offers shall be recorded on the face of envelope and all the members of bid opening committee shall initial with date

16.3.3	First the outer envelope containing the two envelopes will be opened. The bid opening committee shall put initials on all two envelopes with date.

    - Among these two envelops, the envelope marked “Qualifying Bid’’ shall be opened first   and examined.

    - The bidders who have submitted proper bid security as per Tender document, their  “QUALIFYING BID’’ shall be opened and papers/ documents submitted by the bidder shall be examined and recorded by the TOC. After opening the qualifying bid all the documents contained therein shall be serially numbered and signed by the bid opening committee members.

    - After recording of the ``Qualifying Bid’’ the TOC will place all the financials bids submitted by the bidder in an envelope and will seal it with wax for keeping in safe custody.

16.3.7	 The Financial bid shall be opened in the following manner;

16.3.8	  The envelope marked ``Financial Bid’’ will be opened only for qualified Tenders in

``Qualifying bid’’

16.3.9	The date and time of opening of ``Financial bid’’ shall be conveyed to all the bidders who have qualified in Qualifying Bid and their representative shall be allowed to attend the financial bid opening.

16.3.10  After opening the ``Financial Bid’’ the bidders name, bid prices modification, bid withdrawals and such other details as the department, at  its discretion, may consider appropriate ;will be announced at the opening

16.3.11    In case there is discrepancy in figures and words in the quote, the same shall be announced in the bid opening, but the rate quote in words shall prevail.

17.	CLARIFICATION OF BIDS BY THE BSNL:

To assist in examination, evaluation and comparison of bids, the BSNL may at its discretion ask the bidder for clarification of its bid. The request for its clarification and its response shall be in writing. However no post bid clarification at the initiative of the bidder shall be entertained.

18.	   Preliminary evaluation:

18.1            BSNL shall evaluate the bids to determine whether they are complete, whether any computational errors have been made, whether required sureties have been furnished, whether the documents have been properly signed and whether the bids are generally in order.

18.2	 If there is discrepancy between words and figures, the amount in words shall prevail.  If the contractor does not accept the correction of the errors, his bid shall be rejected.

18.3	Prior to the detailed evaluation, pursuant to clause 21, the BSNL will determine the substantial responsiveness of each bid to the bid document. For purpose of these clauses a substantially responsive bid is one which confirms to all the terms and conditions of the bid documents without deviations. The BSNL determination of bids responsiveness is to be based on the contents of the bid itself without recourse to extrinsic evidence;

18 .4  	A bid determined as substantially non responsive will be rejected by the BSNL and shall not subsequent to the bid opening be made responsive by the bidder by correction of the non-conformity.

18.5  	The BSNL may waive any minor infirmity or non-conformity or irregularity in a bid which does not constitute a material deviation, provided such waiver does not prejudice or affect the relative ranking of the bidder.

- EVALUATION AND COMPARISON OF SUBSTANTIALLY RESPONSIVE BIDS:

  - The BSNL shall evaluate in detail and compare the bids previously determined to be substantially responsive pursuant to clause 18.

  - The evaluation and comparison of responsive bids shall be done in accordance with amount worked out based on Evaluation Criteria (on over all L1 basis).  The L1, L2, L3 etc will be finalized based amount calculated in Evaluation Criteria.

- CONTACTING THE BSNL:

  - Subject to clause 17 no bidder shall try to influence the BSNL on any matter relating to its bid, from the time of bid opening till the time the contract is awarded.

  - Any effort by the bidder to modify his bid or influence the BSNL in the bid evaluation, bid comparison or the contract award decisions that shall result in the rejection of the bid.

- AWARD OF CONTRACT:

  - The BSNL shall consider award of contract only to those eligible bidders whose offer have been found Technically, Commercially and Financially acceptable.

- BSNL RIGHT TO VARY QUANTUM OF WORK:

The BSNL, at the time of award of work under the contract, reserves the right to decrease or increase the total quantum of work specified in the schedule of requirements by ± 25% without any change in the rates or other terms and conditions.

- BSNL’s RIGHT TO ACCEPT ANY BID AND REJECT ANY OR ALL BIDS:

23.1    The BSNL reserves the right to accept or reject any bid and to annul the bidding process and reject all bids, at any time prior to award of contract without assigning any reason what-so-ever and without thereby incurring any liability to the affected bidder or bidders on the grounds for the BSNL action.

  - The Tender approving authority is not bound to accept the lowest Bid.

24        ISSUE OF LETTER OF INTENT:

  - The issue of letter of intent shall constitute the intention of the BSNL to enter in to the contract with the bidder. Letter of intent will be the issued as offer to the successful bidder.

  - The bidder shall with in 21 days of issue of letter of intent, give his acceptance along with performance security in conformity with cause 5(i) section- V, provided with the bid documents.

- SIGNING OF AGREEMENT:

  - The signing of agreement shall constitute the award of contract on the bidder. The agreement with the successful bidder shall be signed with in a week by the BSNL after contractor supplying the required Performance Security and material security as per associated clauses of Tender document.

  - As soon as the Tender is approved by the competent authority, the Bid Security deposited by the successful bidder shall be compulsorily converted into the performance security deposit, which will be held by the BSNL till the completion of warranty period.

  - "In the event of failure of the Bidder to sign the Agreement within seven days of being called upon to do so or in the event of his failure to start the work as stipulates the amount of Earnest Money shall stand forfeited and the acceptance of the Bid shall be re-considered and revoked which will not amount to imposing of penalty."

- ANNULMENT OF AWARD:

Failure of the successful bidder to comply with the requirement of clause 25 shall constitute sufficient ground for the annulment of the award and forfeiture of the bid security, in which event the BSNL may make the award to any other bidder at the discretion of the BSNL or call for new bids.

SECTION – V

GENERAL (COMMERCIAL) CONDITIONS OF THE CONTRACT

1.	APPLICATION:

The General Conditions shall apply in contracts made by the BSNL for the execution of O F cable construction works.

2. 	STANDARDS:

The works to be executed under the contract shall conform to the standards prescribed in the O F Cable construction   practices.

3.	PRICES:

3.1	Prices charged by the contractor for the works performed under the contract shall not be higher from the prices quoted by the contractor in his Bid.

3.2	Price once fixed will remain valid for the period of contract. Increase and decrease of taxes / duties will not affect the price during this period.

4.	SUBCONTRACTS:

The contractor shall not assign, sub contract or subject the whole or any part of the works covered by the contract under any circumstances.

5	SECURITY:

5. (i)	MATERIAL SECURITY:

a.	The successful Tenderer will have to deposit material security as mention in the scope of work, subject to minimum of Rs 2.0 lacs, in the form of bank guarantee (valid up to and including six month after, the period of contract)from a scheduled bank and in the material security bond form provided in the bid document, section-IX. Material security can also be submitted in the form of crossed demand draft drawn in favor of Account officer (Cash) O/O GMTD Solan issued by a schedule bank and payable at Solan. The material security will be a non interest bearing deposit for any period what so ever.

b.	The contractor at any point of time will not be issued stores costing more than material security, if due to any reason more store has to be issued to the contractor, then material security will be suitably enhanced. In this regard the decision of The GMTD Solan shall be final and binding.

c.	The process of material security shall be payable to the BSNL as compensation for any loss resulting from the contractors failure to handle properly the material issued to him under the contract.

d.	The material security shall be released / refunded with in a fortnight from the date of the payment of the last final bill of the work under the contract or final settlement of material account which ever is later on production of no dues certificate from Engineer in charge of work duly countersigned by the DE concerned.

5. (ii)	PERFORMANCE SECURITY:

Performance/risk security @ 10% of total estimated cost of work shall be deposited by the contractor in following ways: -

i) The EMD @ 2.5% deposited by the bidder shall be converted to the performance security.

ii) Remaining 7.5% shall be recovered from the running/final bills.

The proceeds of the performance security shall be payable to BSNL as compensation for any loss resulting from the contractor’s failure to complete its obligation under the contract.

The security deposit shall be refunded with in six months on expiry of the Tender period provided there are no recoveries to be made arising out of poor quality of work, incomplete work and / or violation of any terms and conditions of the contract as stipulated in the bid document after getting the NOC from the SDO Incharge of the work duly countersigned by the D.E. concerned. No interest will be paid to the contractor on the security deposit.

5. (iii)   UNCLAIMED SECURITY DEPOSIT:	Security Deposit(s) that is (are) due for refund to the Contractor/Supplier and remain unclaimed for three years after its/their refund become(s) admissible (for instance, after the contractor/supplier fulfils his contract shall be dealt with in accordance with the provisions contained in the rules of the BSNL.

6.	ISSUE OF WORK ORDERS AND TIME LIMIT:

  - The work order shall be issued so as to include all items of works for the section allotted to the contractor as put in the NIT.

  - The work orders shall be issued by the Divisional Engineer (Planning) or any other Officer designated by GMTD Solan after examining the technical and planning details of the works to be executed and after taking the approval of GMTD Solan.

  - If due to any reason partial work order is to be issued then the same shall be issued with the approval of an officer not below the rank of General Manager.

  - The Divisional Engineer will mention the time limit to execute the work order after seeing the quantum of work and store availability position.

  - The BSNL reserves the right to cancel or modify the scope of work stipulated to be carried out against the work order in the event of change of plan necessitated on account of technical reasons or in the opinion of work order issuing authority or the head of SSA, the contractor is not executing the work at the required pace.

7.         EXTENSION OF THE TIME LIMIT:

  - General

    - In each work order, the work order issuing authority shall specify the time allowed for completion of work consistent with the magnitude and urgency of work. The time allowed for carrying out the work is to be strictly observed by the contractor and shall be reckoned from seventh day from the date of issue of work order.

    - In as much as “the time being deemed to be the essence of contract”, throughout the stipulated period of contract, the work is to be proceeded with all due diligence on the part of the contractor.

  - Application for Extension of the Time and Sanction of Extension of Time (EOT):

    - There may be some hindrances, other than covered under force majeure, while execution of work and in such cases the contractor shall apply in writing in the prescribed Form (Part-A) to the engineer-in-charge for extension of time (EOT), on account of which he desires such extension within three days of occurrence of hindrance. The Engineer-in-charge shall forward the request to the competent authority (an officer of the rank of JAG level in-charge of U/G Cable constructions work) with his detailed report and photocopy of the hindrance register, in the prescribed From (Part-B) within three days of receipt of request from the contractor. The competent authority is empowered to grant extension of time for completion of work on certain conditions. He shall exercise such powers, if the following conditions are satisfied.

7.2.1.1.	The application contains the grounds which hindered the contractor in execution of work.

      - The Engineer-in-charge is of the opinion that the grounds shown for extension of time are reasonable.

7.2.2.	The competent authority shall consider the request keeping all the facts and circumstances in view and shall grant extension of time, if in his opinion, there are reasonable and sufficient grounds for granting such extension and the reasons for delay are not ascribable to the contractor.

7.2.3.	The competent authority may also grant extension of time for completion of work in cases where reasons for delay are ascribable to the contractor, but such extension of time shall be with LD charges as per clause dealing with penalty for delays in execution of works. The extension of time with LD charges shall be issued under the signature of JAG level Telecom Officer competent to grant the extension of time.

    - The competent authority shall grant EOT with time period for completion of work expressly mentioned. The sanction of the competent authority of EOT shall be issued under the signature of the Engineer-in-charge.

    - If the competent authority is of the opinion that the grounds shown by the contractors are not reasonable and sufficient and declines to grant the extension of time, the contractor cannot challenge the soundness of the opinion by reference to arbitration. The decision of the competent authority on period of extension of time or refusal for extension of time shall be final and binding on the contractor.

  - Grant of Extension of Time without Applications:

7.3.1   There are, at times, practical difficulties like non-availability of materials, delay in providing, permissions/right of way etc. reasons of which are ascribable to the BSNL. In such cases, the Engineer-in-charge with the approval of competent authority to sanction EOT, may issue extension of time without waiting for contractor to make an application for EOT. Entry of hindrances shall be made in the Hindrance Register. The BSNL will, however, not be liable to the contractor for any losses or damages, costs, charges or expenses that the contractor may in any way sustain/suffer due to delay in making the above available.

8.	 MEASUREMENT, INSPECTION, TESTING AND ACCEPTANCE TESTING:

8.1	MEASUREMENT:

8.1.1	The measurement books are to be maintained by the officer in-charge of the work or his immediate engineering subordinate not below the rank of Junior Telecom Officer.  The entry shall be made in ink.  No entry shall be erased.  If a mistake is made, it should be corrected by crossing out the incorrect words or figures and inserting the corrections, the corrections thus made shall be initialed & dated by the officer concerned.

8.1.2	Responsibility of taking and recording measurement:  The measurement of various items of work shall be taken and recorded in the measurement book issued with each work order.  The measurement of various items of work shall be taken and recorded by an officer not below the rank of Junior Telecom officer, supervising the work. The Junior Telecom Officer /Sub Divisional Engineer, directly responsible for supervision of work, shall be responsible for accuracy of 100% of measurements.  The Sub Divisional Engineer where Junior Telecom Officer is Supervising officer shall be responsible for conducting test check of 50% of measurements.  The Divisional Engineer shall be responsible for conduction test check of 10% of measurements.

8.1.3	Method of recording of nomenclature of items:  Complete nomenclature of items, as given in the agreement need not be reproduced in the measurement book for recording the measurements but corresponding items code as provided shall be used.

8.1.4	Method of measurements:  The measurements of the work shall be done for activity wise as and when the item of work is ready for measurement.  The methods of measurement of various items are enumerated as under.

- Measurement of depth of trenches

The cable routes of one work order shall be divided into number of segments each of maximum 200 meters length bounded by identifiable landmarks at both the ends of the segments.  If landmarks are not available, length of segment may be maintained at 200 meters.  One segment shall cover only one type of trench.  The measurement of depth shall be recorded at each point of measurement (POM) in the measurement book in    meters in the multiples of 5 cms. For example 97 cms will be recorded as 95 cms and103 cms as 105 cms. The point of measurements shall be at a distance of 10 meters starting from 0 (Zero) meter.  For example, if the length of segment is 75 meters, the POMs shall be at 0 M, 10M, 20M, 30M, 40M, 50M, 60M, 70M.The last POM shall be at 75th m to be recorded against residual POM . The efforts required to excavate trenches is not proportionate especially with reference to

depth. Therefore, normally the workers tend to dig shallow trenches .As standard depth of the trench is important for future life and protection of cables, this tendency has of be discouraged. In order to encourage the contractor to achieve best possible depth in the face of site constraints the following scale of payment shall be applied for digging trenches of lesser depths, subject to condition that relaxation has been granted by the competent authority for lesser depths.

| Depth between | Reduction in Rate |
| --- | --- |
| <165 Cms. to ≥ 150Cms. | 5% of approved rate |
| <150Cms. to ≥ 130 Cms. | 12.5% of approved rate |
| <130 Cms. to ≥ 100 Cms | 25% of approved rate |
| Below 100 Cms. | 40% of approved rate |

Following formula will be applied for calculation for payment:

P= [(100-ROR)/100] x RA x (D/ND).

Where:	P   	=    	Payment of one meter in Rs.

ROR		=     	Reduction in Rate in % as per table given above.

RA  		= 	Approved rate of trenching per meter (in Rs.)

D        		 = 	Actual depth achieved in Cms.

ND 		= 	Nominal depth of trench 165 Cms. for which Tender has been floated.

Minimum allowable depth in various cases will be as per clause 8.1.8 (Summary of Laying of OFC)

- Measurement of lengths and profiles of strata and protection The measurements of length of trenches are on running meter basis, irrespective of type of soil encountered while digging.The type of protection provided (item code wise ) in a segment shall be recorded in the measurement book in the sheet provided  for this purpose .

- Measurement of length of cable the length of cables laid in trenches, through pipes and through ducts shall be measured by use of RODO Meter/Measuring Tape. The length should be cross verified with the marking of lengths on the cables. The lengths shall be recorded in sheet provided in the measurement book.

- Measurement of other items the measurement /numerical details of other items shall be recorded in the sheets provided  for respective items viz

  - Digging of joint pit and preparation of joint chamber along with its type i.e. Brick chamber or Pre Cast RCC type.

  - Fixing, painting and sign writing of route /joint indicators.

  - Termination of cable in equipment room and no. of joints

    - The contractor shall sign all the measurement recorded in the measurement book.  This will be considered as an acceptance by the contractor, of measurement recorded in the MB.  In case contractor fails to attend at the measurements or fails to countersign or to record the difference with in a week than in any such events the measurements taken by Engineer-in-charge or by the subordinate as the case may be shall be final and binding on the contractor and the contractor shall have no right to dispute the same.

    - The Divisional Engineer before passing the bill for section covered by each set of measurement may carry out test check by re-opening trench as many locations as necessary specified in document ‘ procedures for underground cable construction’ and bills will be passed only when he is personally satisfied of other aspects of the work as per the terms of the contract.  The contractor shall provide the necessary assistance of labour for re-opening of trench for test check by the Divisional Engineer.  Separate payment shall not be made to the contractor for excavation of such test checks; however such test pits shall not be more than 10% of the cable laying work.

    - Measurement of the work of cable pulling through pipe /duct will be taken equal to the length of the pipe /duct through which the cable has been pulled and not the total length of the cable pulled through pipe /duct.

SUMMARY OF TYPE OF PROTECTION REQUIRED FOR LAYING PRACTICE FOR OPTICAL FIBRE CABLE

| S.No. | Depth (In Centimeters) | Type of Protection required |
| --- | --- | --- |
| 1. | 50cms to 89cms | Reinforced concrete casing 4" |
| 2. | 90cms to 119cms | DWC / RCC |
| 3. | 120cms to 165cms | No Protection is required |

*	The relaxation in laying of OFC for depth from 90cms to 164cms can be granted

by DGM Solan on recommendation of DET concerned.

**	The relaxation in laying of OFC for depth below 90cms to 50 cms can be granted by CGMT HP Telecom Circle Shimla on recommendation of GMTD Solan.

*** 	The depth below 50cms is not permissible.

****	SDE Incharge of the work must ensure that proper prior intimation is given to the competent authority for less depth relaxation during the execution of work so that site may be visited in time.

| S. No. | On culvert/bridges/Rail /Road crossing. |
| --- | --- |
| 1. | Nallah dry for nine months in a year. | 1.5M below the bed of Nallah. | PLB pipe in side RCC/DWC pipe | As per detail in Fig 4(a). |
| 2. | On culvert / bridges /over other Nallahs. | No particular depth specified. | Various options are available as depicted in Fig.4 (a) to 4(g) | The laying is done as per direction of Engineer in-charge. |
| 3. | Rail bridge /crossing | 1.5M | PLB pipe in side cast iron pipe | As per detail in Fig 3(b). |
| 4. | On road crossing | 1.5M | PLB pipe inside RCC/DWC pipe /GI pipe | The laying is done as per direction of Engineer in-charge. |

  - Inspection, and Quality Control:

8.2.1	The Quality of Works:	The importance of quality of Optical Fibre cable construction works can not be over-emphasized. The quality and availability of long distance media and efficiency of the reliable media connectivity to exchanges depends up on quality of laying of Optical Fibre Cable. Further the OF cables are vulnerable to damages due to work of other agencies.

8.2.2    The quality of O.F. cable plant depends upon the quality of individual items of work involved viz Depth of Cables laid, care while paying & laying, Protection Jointing of Cables and Termination in equipment room and at last but not the least on documentation of cable network. In order to ensure quality in cable construction work, each component of work needs attentions. The works shall be carried out strictly in accordance with specification laid down to achieve the requisite quality aim.

8.2.3	It is imperative that the contractor (s) is/are fully conversant with the construction practices and shall be fully equipped to carry out the work in accordance with the specification. The contractors are expected and bound to ensure quality in construction works in accordance with specifications laid down.  The contractor shall engage adequate and experienced supervisors to ensure that works are carried out as per specifications and with due diligence and in professional manner. The contractors shall satisfy himself/ themselves that the work conforms to the quality specifications before offering the same to A/T. Wing for acceptance and Testing.

    - An assessment of extent of interest shown by the contractors in executing the works with requisite quality shall be recorded and used in evaluating the contractor’s Performance Rating (CPR).

    - In addition to Acceptance Testing being carried out by A/T. Wing and supervision by construction Officers, all works at all times shall be open to inspection of the BSNL. The contractors shall be bound, if called up on to do so, to offer the works for inspection without any extra payment.

    - Site Order Book:   The site order book is on of the primary records to be maintained by the JTO supervising the work during the course of execution of works.  The noting made by officers as will as contractor will form as basis for operation of many Contractual clauses. The Contractor shall remove all the defects pointed out by the department in the site order book.  The site order book is to be maintained in the prescribed format.  The contractor or their authorized representatives shall also be at liberty to note their difficulties etc. in these books. The site order books shall invariably be consulted at the time of making final payments to the contractor.

  - Testing and Acceptance Testing :

    - The work shell be deemed to have been completed only after the same has been accepted by the A/T officer. The contractor shall make test pits at the locations desired by A/T officer for conducting test checks without any extra payment. The contractor shall restore the pits after test measurement to its original shape. The contractor shall be responsible to provide test/measurement tools and testers conducting various tests.

    - Scope of acceptance and testing: The purpose of acceptance and testing is to verify integrity of measurement and quality of work done. The A/T. officer shall not be responsible by the recording of measurement for the purpose of billing and contractual obligations. However, if the measurement taking by A/T Officer are found to be lesser than the measurement recorded by the officer responsible for recording the measurement, the measurement taken by A/T Officer shall prevail with out prejudice to any punitive action against the contractor as per provisions of the contract and the officer recording the measurement.  The contractor shall be obligated to remove defects /deficiencies pointed out by the A/T Officer with out any additional cost  to the department .

    - Offering the work for acceptance and testing:  The Sub Divisional Engineer responsible for construction, after having satisfied himself of completion of work ready for A/T, shall offer the work to A/T Officer for conducting acceptance and testing. The work shall be offered for A/T as soon as part of work is complete in all respects the work against any work order can be offered for A/T in a number of such stages.

    - The contractor shall provide labour, if demanded by the A/T Officer for digging of test pits and other necessary infrastructure for carrying out the A/T work. No extra payment will be made for the digging of test pit

    - WARRANTY :

9.1	The contractor shall warrant that the material supplied for the work shall be new and free from all defects and faults in material , workmanship and manufacture and shall be of the highest grade and consistent with the established and generally accepted standard for  material of the type ordered and shall perform in full conformity with the specification  and drawing . the contractor responsible for any defects that may develop under the conditions provided by the contract and under proper use , arising from faulty materials , design or workmanship such as corrosion of the equipment inadequate quantity of material etc .and   remedy such defects at his own cost when called upon to do so by the department who shall state in writing in what respect the store are faulty , this warranty shall survive inspection or payment for, and acceptance of goods, but shall expire except in respect of complaints notified prior to such date, twelve months after the acceptance  testing .

9.2	If it becomes necessary for the contractor to replace or renew any defective portion /portions of the material under this clause, the provisions of the clause shall apply to the portion /portions material so replaced or renewed or until the end of the above mentioned period of twelve months, whichever may be later. If any defect is not remedied within a reasonable time, as prescribed by the department, the department may proceed to do the work   at the contractor’s risk and costs, but without prejudice to any other rights which the Department may have against the contractor in respect of such defects.

  - The Cable joint shall be guaranteed for a period of ONE year from the date of closing of joint .In case of failure of the joint due to poor workmanship i.e. failure of joint without external damage, with in the stipulated period of guarantee the contractor shall repair the joint (s) at his own cost within 24 hours of informing him, failing which the department may carry out the repairs and penalty equivalent to five times of the approved rate of the jointing work plus the cost of materials  used shall be recovered from the contractor from his pending bill/SD or any amount due to him without prejudice to any other action as per terms and conditions of the Tender. The cost of jointing kit, supplied by the BSNL, so used to revive the joint shall be deducted from the bills of the contractor pending for payment or from security if all bills have been settled.

  - Replacement under warranty clause shall be made by the contractor free of all charges at site including freight, insurance, cost of works and the incidental charges.

10.       AUDITS AND TECHNICAL EXAMINATION:

  - BSNL shall have the right to cause an audit technical examination of the work and the final bills of the contractor including all supporting vouchers, abstract etc. to be made after payment of the final bill and if as a result of such audit and technical examination any sum is found to have been overpaid in respect of any work done by the contractor under the contract or any work claimed by him to have been done by him under the contract and found not to have been executed, the contractor shall be liable the refund the amount of over payment and it shall be lawful for BSNL to recover the same from him in the manner prescribed in clause with the heading payment of bills (Same chapter), or in any other manner legally permissible and if it is found that the contractor was paid less than what was due to him under the contract in respect of any work executed by him under it, the amount of such under payment shall be duly paid by BSNL to the contractor.

  - Provided that BSNL shall be entitled to recover any sum overpaid, nor the contractor shall be entitled to payment of any sum paid short where such payment have been agreed upon between the Divisional Engineer or his subordinate officer on one hand and the contractor on the other under any term of the contract permitting payment for work after assessment by the GMTD Solan or his subordinate officer.

  - Any sum of money due and payable to the contactor (including security deposit returnable to him) under this contact may be appropriate by the BSNL for the payment of a sum of money arising out or under any other contract made by the contractor with the BSNL.

11.	      PAYMENT TERMS:

  - Procedure for preparation and settlement of bills:

Each claimed bill of contractor must accompany:

  - The list showing the details of labourers /employees engaged

  - Duration of their engagement.

  - Amount of wages paid to each such labourer/employee for the duration in question.

  - Amount of EPF contributions (both employer’s and employee’s contribution),

  - Copies of authenticated documents of payments of such contribution to EPF authorities and

  - A declaration from the contractor regarding compliance of conditions of EPF Act 1952.

      - All items of work involved in the work order shall be completed in all respects before preparing the bills for the work. The provision of running bill has been made to make it easy for the contractor to manage his cash flow and to complete the work systematically and meaningfully in a shortest possible time. The procedure for preparation of running and final bills is enumerated as under:

      - Procedure for preparation, processing and payment of running bills:

The contractor shall prepare the running bills in triplicate ensuring execution of part work in its completeness as envisaged above, correctness of rates and quantum of work and submit the bills to SDE in-charge of work. The bills shall be prepared accurately and as per measurements recorded in the measurement book. The SDE in-charge shall record the certificate on the running bill that the site order books have been consulted before signing the running bills. This would enable the SDE to ensure whether the defects pointed during execution have been rectified or not. The SDE in-charge of work shall scrutinize the bills and accord necessary certificates and submit the running bills with the documents as mentioned below to the Divisional Engineer, in-charge of work.

*	First copy of bill with first copies of measurement sheets of measurement book (payable copy)

*	Second copy of bill with second copies of measurement sheets of measurement book (Not for payment)

*          Third copy of the bill with photocopies of measurement sheets (Not for

Payment)

      - The Divisional Engineer shall exercise the prescribed checks on the bills and accord necessary certificates on the bills. The Divisional Engineer shall retain the third copy in record and record it in the estimate file maintained in his office and send first and second copies with all documents to relevant higher office for processing of bills and release of payment.

      - The office cell dealing with bills shall process the bills in the estimate file of the concerned work and scrutinize the bills vis-à-vis work order issued, sanctioned provisions in the estimate etc. The officer competent to pass the bill shall pass the bill, after necessary scrutiny by works section. Amount passed in the bill will be issued only after the contractor gives a stamped receipt for the amount, if the bills are not pre-receipted. Details of payment of all the bills shall be entered into contracts ledger by work section of the planning cell.

      - In exceptional cases where work required for preferring a running bill can not be completed within reasonable time due to non-availability of stores or any other reason and where the BSNL is responsible for delay, the GMTD may permit payment of running bill (prepared without completing the work end-to-end for that unit of work) to the extent of 70% so that the contractor does not face resource crunch. Such payment shall be treated as an advance payment to the contractor like any other running bills.

    - Procedure for preparation, processing and payment of final bill: The contractor shall prepare the final bill in triplicate & acceptance and testing of all the works and submit the same to SDE in-charge of work within 30 days of acceptance and testing and payment shall be made within three months if the amount of the contract is up to Rs. Two lac and in six months if the same exceed Rs. Two lacs, of the submission of such bill. The final bill shall be prepared for all the measurements of all items involved in execution of complete work order. The contractor shall prepare the final bill containing the following details:

*	The bill for all the quantities as per measurements at the approved rates

*	Store reconciliation statement furnishing account of stores received against the work order and returned to the designated store godown as surplus with requisite verifications from store in-charge/SDE in-charge of work.

*	Letters of grant of EOT(s). If work could not be completed within stipulated time.

*         Three sets of bound documentation.

      - The SDE in-charge of work shall scrutinize the final bill against the works entrusted and accord necessary certificates starting that the work has been executed satisfactorily in accordance with specifications and terms and conditions of the contract. The SDE shall verify the quantities of items of work with reference to measurements recorded in the measurement book (and also A/T reports in case of any deviations noted by A/T officer). The SDE in-charge of work shall submit the final bills, along with other documents mentioned above, with the documents as mentioned here under to the Divisional Engineer, in-charge of work.

* Bill prepared by the contractor

* Material reconciliation statement

* Measurement book

* A/T certificates

* Details of recoveries/penalties for delays, damages to BSNL/ Third party  properties as per provisions of the contract. In case no recovery is to be made, NIL report needs to be submitted.

* Details of empty cable drums cost which needs to be recovered from the bill.

      - The Divisional Engineer shall exercise the prescribed checks on the bills and accord necessary certificates on the bills. The Divisional Engineer shall retain the third copy of the bill along with photocopies of other documents not available in his estimate file and send first and second copies of the bill, measurement book and other documents submitted by SDE along with the bills as above to the higher office for processing and final payment.

      - The office cell dealing with bills shall process the bills in the estimate file of the concerned work and scrutinize the bills vis-à-vis work order issued, sanctioned provisions in the estimate etc. The office cell shall also scrutinize the bill to recover all the liabilities of the contractor and TDS .The officer competent to pass the final bill shall pass the bill, after necessary scrutiny by works section.

  - Procedure for payment for sub standard works:

    - The contractors are required to execute all works satisfactorily and in accordance with the specifications. If certain items of work are executed with unsound, imperfect or unskilled workmanship or with materials of any inferior description or that any materials or articles provided by him for execution of work are unsound or of a quality to that contracted for or otherwise not in accordance with the contract (referred to as substandard work hereinafter), the Divisional Engineer in-charge shall make a demand in writing specifying the work, materials or articles about which there is a complaint.

    - Timely action by construction officers: Timely reporting and action, to a great extent, can prevent occurrence of sub standard work, which will be difficult or impossible to rectify later on. It is incumbent on the part of construction officers to point out the defects in work in time during progress of the work. The Junior Telecom Officer/ Sub Divisional Engineer responsible for execution and supervision of work shall without any loss of time submit a report of occurrence of any sub standard work to the Divisional Engineer in-charge besides making an entry in the site order book. A notice in respect of defective work shall be given to the contractor by Divisional Engineer in-charge in writing during the progress of work asking the contractor to rectify/replace/remove the sub standard item of work and also definite time period within which such rectification/removal/replacement has to be done. After expiry of the notice period, if the contractor fails to rectify/replace/. Remove the sub standard items; the defects shall be got rectified/replaced/removed departmentally or through some other agency at the risk and cost of the contractor.

    - Non-reporting of the sub standard work in time on the part of construction officer(s) shall not in any way entitle the contractor to claim that the defects were not pointed out during execution and as such the contractor can not be absolved of the responsibility for sub standard work and associated liabilities.

    - Authority and procedure to accept sub standard work and payment thereof, There may be certain items of work pointed out as sub standard which may be difficult to rectify and in the opinion of the Head of SSA, the items in question will not materially deteriorate the quality of service provided by the construction, the head of SSA shall appoint committee to work out the reduced rates payable to the contractor for such sub standard work. The committee shall constitute one Divisional Engineer other than the one who is directly in-charge of cable construction involving sub standard items of work, as Chairman and one SDE and an Accounts Officer as member. The committee shall take into account the approximate cost of material /work pointed out as sub standard and recommend the rates payable for sub standard work which shall not exceed 60% of the approved rates of the item in question.

    - Record of sub standard work: The items adjudged, as sub standard shall be entered into the measurement book with red ink.

12.		            DISPOSAL OF EMPTY CABLE DRUMS:

  - The contractor shall be responsible to dispose off the empty cable drums after lying of the cable. The cost of empty cable drums shall be deducted from the bill for the work on which the cable along with the drum has been issued or any other amount due to the contractor or from security deposit.

  - Rates fixed for empty u/g Cable drums are given in Tender Document. The rates are fixed and there is no percentage above or below applicable on these rates.

  - The contractor shall be responsible for the accounting of the cable drums issued and shall mention the number of empty cable drums in the bill so that the amount is deducted from the bills due.

  - The contractor shall not be allowed to dump the empty cable drums in Govt./public place, which may cause inconvenience to Govt./Public. If the contractor does not dispose off the empty cable drums with in 3 days of becoming empty, the BSNL is at liberty to dispose off the drum in any manner deemed fit and also recover the amount fixed in this contract for empty cable drums along with the transportation charges (to be decided by GMTD Solan) from the bill/security deposit/ any other amount due to the contractor.

13.		             PENALTY CLAUSE:

  - Delays in the contractors performance:

13.1.1 	The time allowed for completion of the work as entered in the Tender shall be strictly adhered by the contractor and shall be deemed to be the most important aspect of the contract on the part of the contractor and shall be reckoned from Seventh day from issue of work order by the BSNL The work shall, throughout the stipulated  period of contract, be proceeded with all due diligence to achieve the desired progress uniformly  and the contractor shall pay as penalty an amount equal to 1.0 ( one ) percent of the amount (minimum Rs One thousand per week) of the incomplete work for every one week of delay in completion of work, subject to a maximum of 10 (ten) percent of the cost of the work awarded.

    - On any date the penalty payable as above, reaches 10 (ten) percent of the estimated cost of the work, the contractor should proceed with the work further only on getting a written instructions from the Divisional Engineer that, he is allowed to proceed further with the work. It will be in the discretion of the Divisional Engineer to allow the contractor to continue with the work on the basis of any written agreement reached between the contractor and he Divisional Engineer one of the conditions of such agreement may be a stipulation for the contractor to agree for realization of penalty for delay at a higher rate as may be agreed between the Divisional Engineer and contractor.

    - Penalty for delay in completion of the work shall be recoverable from the bills of the contractor and/or by adjustment from the security deposit or from the bills of any other contract. However, adjustment from security deposit will be made only when the contract has been terminated or at the time of final settlement of bills on completion of work.

    - In case of slow progress of the work in a section which have been awarded to a particular contractor, and the public interest does not permit extension of time limit for completion of the work .The GMTD Solan will have the full right to order that the scope of the contractor may be restricted to such fraction of the whole of the work and get the balance executed at the risk and cost of the contractor. The details are given in Rescission of the contract clause of the bid document. All such payments shall be recovered from the contractors pending bills or security deposit.

    - The GMTD Solan reserves the right to cancel the contract and forfeit the security deposit if the contractor fails to commence the work within 7 days after issue of the work order.

  - Penalty for causing inconvenience to the public:

    - To ensure progress during the execution of work and to cause minimum inconvenience to the public, the contractor shall not dig a trench of more than 200 meters at a stretch in a route at a time. He shall cause to lay cable and close such trenches expeditiously. Under any circumstances a stretch of trench of minimum 200 meters shall not be kept open for more than 4 days in case of cable lying by digging paved surfaces. In the event of contractor falling to comply with, these conditions, the BSNL may impose a penalty of recovery up to Rs. 300/- per day the trench is kept open beyond the time limit allowed. This penalty will be in addition to that payable for delay or slow work.

    - The contractor shall not be allowed to dump the empty cable drums/waste materials in Govt./public place, which may cause inconvenience to Govt./Public. If the contractor does not dispose off the empty cable drums/waste materials within 3 days of becoming empty, the BSNL is at liberty to dispose off the drum in any manner deemed fit and also recover the amount fixed in this contract for empty cable drums/waste materials from the bill/security deposit/along with the costs incurred by the BSNL in disposing off such materials. The BSNL may also levy a penalty up to Rs. One thousand for each such default.

    - If any such penalty is levied on a contractor for more than 2 occasions, then his/her contract could be terminated. In this regard the decision of GMTD Solan shall be final and binding.

  - Penalty for cutting/damaging the old cable:

    - During excavation of trench utmost care is to be taken by the contractor, so that the existing underground cables are not damaged or cut. In-case any damage /cut is done to the existing cables, a penalty as per the schedule given below will be charged from the contractor or the amount will be deducted from his bills.

| Size of existing U.G. /OF cables cut/ damaged | Amount of penalty per cut/damage |
| --- | --- |
| Up to 100 pairs cable | Rs. 500/- (Five hundred) |
| Above 100 pairs & up to 400 pairs | Rs. 1000/- (One thousand) |
| Above 400 pairs | Rs. 2000/-(Two thousand) |
| OF Cable of any size | Rs.50000/- (Fifty thousand) |

Besides the above penalty, the contractor shall carry out such repairs for restoration of the damaged cable free of charge. The cost of jointing kit shall also be borne by the contractor. If contractor fails to repair the damage, the cost of repair (including cost of labor + jointing kit) shall be recovered from the contractor.

13.4	Penalty to damage stores/materials supplied by the BSNL while laying:

13.4.1.	The contractor while taking delivery or materials supplied by the BSNL at the designated place shall thoroughly. Inspect all items before taking them over. In case of execution of the work, if any material is found damaged/working unsatisfactorily, then a penalty equivalent to the cost of material + 10% as penalty shall be recovered from the contractors payments/securities.

13.4.2. In case of damage to PIJF cables, while laying, the cost of number of pairs damaged including laying charges, transportation/storage charges adding 10% as penalty shall be recovered from the contractor’s bills securities.

13.4.3	However, contractor will not be penalized for any defect in workmanship of the materials, which shall be taken up separately with the supplier of the stores.

14.	      Rescission/Termination of contract:

14.1	Circumstances for rescission of contract: Under the following conditions the competent authority may rescind the contract.

a)	If the contractor commits breach of any item of terms and conditions of the contract.

b)	If the contractor suspends or abandons the execution of work and the engineer in-charge of the work comes to conclusion that work could not be completed by due date for completion or the contractor had already failed to complete the work by that date.

- If the contractor had been given by the officer-in-charge of work a notice in writing to rectify/ replace any defective work and he/she fails to comply with the requirement within the specified period.

  - Upon rescission of the contract, the security deposit of the contractor shall be

liable to be forfeited and shall be absolutely at the disposal of the Government as under:

    - Measurement of works executed since the date of last measurement and up to the date of rescission of contract shall be taken in the presence of the contractor or his authorized representative who shall sign the same in the MB. If the contractor or his authorized representative do not turn up for joint measurement, the measurement shall be taken by the officer authorized for this purpose after expiry of due date given for joint measurement. The measurement taken by the officer so authorized shall be final and no further request for joint measurement shall be entertained.

    - The unused material (supplied by the BSNL) available at site shall be transported back by the contractor. To the telecom store at his risk and cost .If any such material is found damaged/lost then the penalty shall also be recovered from the contractor as per conditions in Tender documents ibid.

    - The un-executed work shall be got executed through the qualified bidder from amongst the bidders, who participated in the bidding process, by giving them offers in their order of ranking (L2, L3--) at their quoted rates. If the work was awarded on single Tender basis then the BSNL shall get the unexecuted work completed through any other contractor approved in the SSA at the approved rates of that particular section or to execute the work departmentally, as is convenient or expedient to the BSNL at the risk and cost the contractor. In such an event no compensation shall be payable by the BSNL to the contractor towards any inconvenience/loss that he may be subjected to as a result or such an action by the BSNL. In this regard the decision of (GMTD Solan) shall be final and binding. In all these cases, expanses which may be incurred in excess of the sum which would have been paid to the original contractor if the whole work had been executed by him shall be born and paid by the original contractor and shall be deducted from any money due to him by the BSNL under the contract or any other account whatsoever any where in the BSNL or from a security deposit.

    - The certificate of the Divisional Engineer in-charge of work as to the value of work done shall be final and conclusive against the contractor, provided always that action shall only be taken after giving notice in writing to the contractor.

  - Termination for insolvency:

    - The BSNL may at any time terminate the contract by giving written notice to the contractor, without compensation to contractor, if the contractor becomes bankrupt or otherwise insolvent as declared by the competent court provided that such termination will not prejudice or affect any right or action or remedy which has accrued or will accrue thereafter to the BSNL.

14.4	Optional Termination by Government (Other than due default of the contractor):

    - The Government may, at any time, at its option cancel and terminate this contract by written notice to the contractor, in which event the contractor shall be entitled to payment for the work done up to the time of such cancellation and a reasonable compensation in accordance with the contract prices for any additional expenses already incurred for balance work exclusive of purchases and/or whole of material, machinery and other equipment for use in or in respect of the work.

    - In the event of the termination of the contract, the contractor shall forthwith clear the site of all the contractors’ materials, machinery and equipments and hand over possession of the work/operations concerned to the Government or as the Government may direct.

    - The BSNL may, at its option, cancel or omit the execution of one or more items of work under this contract and may part of such items without any compensation whatsoever to the contractor.

14.5	Issuance of Notice:

    - The Divisional Engineer in-charge of work shall issue show cause notice giving details of lapses, violation of terms and conditions of the contract, wrongful delays or suspension of work or slow progress to the contractor directing the contractor to take corrective action. A definite time schedule for corrective action shall be mentioned in the show cause notice. If the contractor fails to take corrective action within the stipulated time frame, the Divisional Engineer in-charge shall submit a draft of final notice along with a detailed report to the competent authority who had accepted the contract.

    - The final notice for rescission of contract to the contractor shall expressly state the precise date and time from which the rescission would become effective. The following safe guards shall be taken while issuing the final notice.

a)	During the period of service of notice and its effectiveness, the contractor should not be allowed to remove from the site any material/equipment belonging to the BSNL.

b)	The contractor shall give in writing the tools and plants he would like to take away/remove from the site. Such of the materials as belong to him and which may not be required for future execution of balance work may be allowed by the Divisional Engineer in-charge of work to be removed with proper records.

c)          No new construction beneficial to the contractor shall be allowed.

- Adequate BSNL security arrangement in replacement of the contractor watch and ward shall be made forthwith. Expenses on this account are recoverable from the security deposit or any amount due to the contractor.

15.	      INDEMNITIES:

15.1	The contractor shall at all times hold the BSNL harmless and indemnify from against all action, suits, proceedings, works, cost, damages, charges claims and demands of every nature and descriptions, brought or procured against the BSNL, its officers and employees and forthwith upon demand and without protect or demur to pay to the BSNL any and all losses and damages and cost (inclusive between attorney and client) and all costs incurred in endorsing this or any other indemnity or security which the BSNL may now or at any time have relative to the work or the contractors obligation or in protecting or endorsing its right in any suit on other legal proceeding, charges and expense and liabilities resulting from or incidental or in connection with injury, damages of the contractor or damage to property resulting from or arising out of or in any way connected with or incidental to the operations caused by the contract documents. In addition the contractor shall reimburse the BSNL or pay to the BSNL forthwith on demand without protect or demur all cost, charges and expenses and losses and damages otherwise incurred by it in consequences of any claim, damages and actions which may be brought against the BSNL arising out of or incidental to or in connection with the operation covered by the contractor.

15.2	The contractor shall at his own cost at the BSNL request defend any suit or other proceeding asserting a claim covered by this indemnity, but shall not settle, compound or compromise any suit or other finding without first consulting the BSNL.

16.		FORCE MAJEURE:

16.1      If any time, during the continuance of this contract, the performance in whole or in part by either party or any obligation under this contract shall be prevented or delayed by reason of any war, or hostility, acts of the public enemy, civil commotion sabotage, fires, floods, explosions, epidemics, quarantine restrictions, strikes, lockouts or act of God (Herein after referred to as events) provided notice of happening, of any such eventuality is given by either party to the other within 21 days from the date of occurrence thereof, neither party shall be reason of such event be entitled to terminate this contract nor shall either party have nay such claim for damages against the other in respect of such non-performance and work under the contract shall be resumed as soon as practicable after such event may come to an end or cease to exist, and the decision of the BSNL as to whether the work have been so resumed or not shall be final and conclusive , provided further that the performance , in whole or part of any obligation under this contract is prevented or delayed by reason of any such event for a period exceeding 60 days either party may, at his option terminate the contract.

  - Provided also that it the contract is terminated under this clause, the BSNL shall be at liberty to take over from the contractor at a price to be fixed by the BSNL, which shall be final, all unused, undamaged and acceptable materials, bought out components and stores in the course of execution of the contract, in possession of the contractor at the time of such termination of such portions thereof as the BSNL may deem fit excepting such materials bought out components and stores as the contract may with the concurrence of the BSNL elect to retain.

17.		ARBITRATION:

17.1	In the event of any question, dispute or difference arising under this agreement or in connection there-with except as to matter the decision of which is specifically provided under this agreement, the same shall be refereed to sole arbitration of the Chief General Manager, HP Telecom circle Shimla or in case his designation is changed or his office is abolished then in such case to the sole arbitration of the officer for the time being entrusted whether in addition to the functions of the Chief General Manager HP Telecom  circle Shimla  or by whatever designation such officers may be called (hereinafter referred to as the said officer) and if the Chief General Manager HP Telecom  circle Shimla or the said officer is unable or unwilling to act as such to the sole arbitration or some other person appointed by the Chief General Manager, or the said officer. The agreement to appoint an arbitrator will be in accordance with the Arbitration and Conciliation Act 1996. There will be no objection to any such appointment that the arbitrator is BSNL Servant or that he has to deal with the matter to which the agreement relates or that in the course of his duties as BSNL Servant he has expressed views on all or any of the matter under dispute. The award of the arbitrator shall be final and binding on the parties. In the event of such arbitrator to whom the matter is originally referred, being transferred or vacating his office or being unable to act for any reasons whatsoever such Chief General Manager to the said officer shall appoint another person to act as arbitrator in accordance with terms of the agreement and the person so appointed shall be entitled to proceed from the stage at which it was left out by his predecessors.

  - The arbitrator may from time to time with the consent of parties enlarge the time for making and publishing the award, subject to aforesaid Indian Arbitration and Conciliation Act 1996 and the Rules made there under, any modification thereof for the time being inforce shall be deemed to apply to the arbitration proceeding under this clause.

  - The value of the arbitration proceeding shall be the office of the Chief General Manager HP Telecom circle Shimla or such other places as the arbitrator may decide. The following procedure shall be followed:

17.3.1	In case parties are unable to reach a settlement by themselves, the dispute should be submitted or arbitration in accordance with contract agreement.

    - There should not be a joint submission with the contractor to the sole Arbitrator.

    - Each party should submit its own claim separately and may oppose the claim put forward by the other party.

    - The onus of establishing his claims will be left to the contractor.

    - Once a claim has been included in the submission by the contractor, a reiteration or modification thereof will be opposed.

    - The “points of defence” will be based on actual conditions of the contract.

    - The Arbitrator shall not entertain claims in the nature of ex-gratia payments, as these are not contractual.

    - The question whether these conditions are equitable shall not receive any consideration in the preparation of “points of defence”.

    - If the contractor includes such claims in his submission, the fact that they are not contractual will be prominently placed before the Arbitrator.

The award of the sole Arbitrator shall be final and binding on all the parties to the dispute.

- SET OFF:

18.1	Any sum of money due and payable to the contractor (including security deposit refundable to him) under this contract may be appropriated by the BSNL or the Govt. or any other person or persons contracting through the Govt. of India and set off the same against any claim of the BSNL or Govt. or such other person or persons for payment of a sum of money arising out of this contract made by the contractor with BSNL or Govt. or such other person or persons contracting through Govt. of India.

SECTION – VI

SPECIAL CONDITIONS OF CONTRACT

1.	      GENERAL:

  - The work shall be accepted only after Acceptance Testing carried out by A/T team, designated by the BSNL, as per prescribed schedule and work/material passing the test successfully.

  - The BSNL reserves the right to disqualify such bidders who have a record of not meeting contractual obligations against earlier contracts entered into with the BSNL.

  - The BSNL reserves the right to black list a bidder for a suitable period in case he fails to honour his bid without sufficient grounds.

  - The BSNL reserves the rights to counter offer price(s) against price(s) quoted by any bidder.

  - Any clarification issued by BSNL, in response to query raised by prospective bidders shall form an integral part of bid documents and it may amount to amendment of relevant clauses of the bid documents.

  - Tender will be evaluated as a single package of all the items given in the financial bid.

  - All work to be executed under the contract shall be executed under the direction and subject to the approval in all respects of by the Divisional Engineer or Site Engineer in-charge of work site who shall be entitled to direct at what point or points and what manner they are to be commenced, and from the time to time carried on.

  - The work in each section may be split up between two or more contractors or accept any Tender in part and not entirely if considered expedient by the GMTD Solan.

  - If the contractor shall desire an extension of time for completion of the work on the   grounds of unavoidable hindrance in execution of work or on any other ground he shall apply in writing to the Divisional Engineer within 3 days of the date of hindrance on account of which he desires such extension as aforesaid. In this regard the decision of GMTD Solan shall be final.

  - If at any time after the commencement of the work, the BSNL may feel that execution of whole or part of work, as specified in the Tender is not required to be carried out, then the BSNL shall give notice in writing of the fact to the contractor who shall have no claim to any payment of compensation whatsoever on account of any profit or advantage which he might have derived in consequence of the full amount o the work not having been carried out neither shall he have any claim for compensation by reason of any alterations having been made in the original specifications, drawings, designs and instructions which shall involve any curtailment of the work as originally contemplated.

  - Whenever any claims against the contractor for the payment of a sum of money arises out of or under the contract, the BSNL shall be entitled to recover such sum by appropriating in part or whole the security deposit of the contractor, and to sell any BSNL promissory notes etc., forming the whole or part of such security or running/Final bill pending against any contract with the BSNL. In the event of the security being insufficient or if no security has been taken from the contractor, then the balance or the total sum recoverable as the case may be, shall be deducted from any sum then due or which at any time there after may become due to the contractor under this or any other contract with BSNL should this sum be not sufficient to cover the full amount recoverable the contract or shall pay to BSNL on demand the balance remaining due.

  - No official of Gazetted rank or other Gazetted officer employed in Engineering or administrative duties in   BSNL or any other deptt. of the BSNL of India is allowed to work as a contractor for a period of two years after his retirement from BSNL service without the previous permission of BSNL of India. This contract is liable to be cancelled if either the contractor or any of his employees is found at any time to be such a person who had not obtained the permission of BSNL of India as aforesaid before submission of the engagement in the contractor’s service as the case may be.

  - In the event of the contractor being, adjusted insolvent or going voluntarily into liquidation of having received order or other order under insolvency act made against him or in the case of company, of the passing of any resolution, or making of any order for winding up whether voluntarily or otherwise, or in the event of the contractor failing to comply with any of the conditions herein specified, The GMTD Solan shall have the power to terminate the contract without any notice.

  - Without prejudice to any of the rights or remedies under this contract, if the contractor dies, the GMTD Solan on behalf of the president can terminate the contract without compensation to the contractor. However   GMTD Solan   at his discretion may permit contractors heirs to perform the duties or engagements of the contractor under the contract, in case of his death. In this regard the decision of GMTD Solan shall be the final.

  - In the event of the contractor, winding up his company on account of transfer or merger of his company with any other, the contractor shall make it one of the terms and stipulations of the contract for the transfer of his properties and business, that such other person or company, shall continue to perform the duties or engagement of the contractor under this contract and be subject to his liabilities there under.

  - Interpretation of the contract document:

    - The representative of GMTD Solan and the contractor shall in so far as possible by mutual consultation, try to decide upon the meaning and intent of the contract document. In case of disagreement the matter shall be referred to   GMTD Solan whose decision shall be final. Any change in the contract documents shall be set forth in writing by the representative of the parties hereto. It shall be the contractor’s responsibility to thoroughly familiarize all of his supervisory personnel with the contents of all the contract documents.

    - Notification:

    - The contractor shall give in writing to the proper person or authority with a copy to the Divisional Engineer such notification as may be mandatory or necessary in connection with the commencement, suspension, resumption, performance and/or completion of the contracted work. All notice shall be given sufficiently in advance of the proposed operation to permit proper co-relation of activities and the contractor shall keep all proper persons or authorities involved and advised of the progress of operations through out the performance of the work and/or with such other information and /or supporting figure and data as may from time to time as directed or required.

  - Shut down on account of weather conditions:

    - The contractor shall not be entitled to any compensation whatsoever by reason of suspension of the whole or any part of the work made necessary by the Government or deemed advised on account of bad weather conditions or other Force majeure conditions.

- STORES SUPPLIED BY THE BSNL:

  - At no point of time the contractor shall be issued stores of value more than the contractor material security as per clause 5(i) of section V. If at all the work requires more amount of material to be issued to the contractor, then the security shall suitably be revised before the issue of the store and the contractor, will not have any objection to it.

  - The contractor shall transport (including loading and unloading) all stores issued to him from District Telecom Store, to the site of work at his own cost and risk.

  - All materials supplied to the contractor by the BSNL shall remain the absolute property of BSNL and shall not be removed from site of the work except for use in the work and shall be at all times open to inspection by the representative of GMTD Solan In case the materials like cable and accessories are taken delivery of by the contractor and stored at the site office/store of the contractor such site office/store will also be treated “as site” for this purpose. Any such materials remaining unused at the time of the abandonment, completion or determination of the contract shall be returned to the BSNL at a place informed to him by the BSNL, failing which the cost of the unused materials shall be deducted from the contractors materials security or any of his pending bills or from any other security.

  - The contractor shall be responsible for the transportation of store, storage and safe custody of all material supplied to him by the BSNL, which in the contractor’s custody whether, or not installed in the work. The contractor shall satisfy himself regularly the quantity and quality of the materials supplied to him and he will be responsible for any subsequent deterioration and discrepancy (inclusive of theft) in the quantity/quality of the materials.

  - The contractor shall submit a proper account every month of all the materials supplied to him by the BSNL and those consumed for items of work any discrepancy of difference between the materials issued to the contractor and those consumed in the work as per the “BSNL calculation” (which shall be final) will be charged to the contractor or deducted from his bill at 1.5 times of prevailing standard price including freight, handling charge, storage charges etc.

  - The contractor shall ensure that only the required material is issued to him. Upon completion of work, the contractor shall return to BSNL at the later designated store in good condition, free of charges, any unused materials that were supplied by the BSNL.

3.        EASEMENTS, PERMITS, LICENCES AND OTHER FACILITIES:

3.1	      The contractor shall obtain/provide at his own cost all easements, permits and license necessary to do its work except for the following, which shall be provided by the representative of the GMTD Solan

a)	“Right of User” easements and permits.

b)	Railway and Highway crossing permits including bridge

- Canal/stream crossing permits.

3.2	      The contractor shall be fully responsible for angling and obtaining all necessary easements, permits and licences, for moving all construction equipment, tools, supplied materials and men across Railways & Highways, across public or private road as well as premises of any public utility within the right of user and for bearing all costs that may be incurred in respect of the same.]

  - The contractor is to confine his operation to the provided construction “Right of User” unless it has made other arrangement with the particular property owners and /or tenants such other arrangements shall be entirely at the responsibility of the contractor as to cost and arrangement as also breach and claim and shall be entitled with a copy to the Divisional Engineer.

  - The contractor will not be entitled to extra compensation for hardship and increase in cost by the cable trench being routed adjacent to or across other pipeline, Highways, Railways, telephones or poser poles and wires or guy wires, embankments, cliffs, streams or other obstacles which may physically or otherwise in any manner, restrict or limit the use of the construction “Right of User”. Some construction and such contingency shall be deemed to have been providing for in the rates.

  - At location where the u/g cable trench is routed across or along roads the contractor shall without extra cost provide and maintain such detours and road controls as are required by the  local agencies having jurisdiction.

  - If the BSNL is not able to provide above mentioned permits etc. in time then the extension of time limit should be provided as per EOT clause given in Tender document.

  - Required way leave permission may be getting from local authorities (National/State Highways, local municipalities etc.) to avoid delay in works.

4.     QUALITY OF WORK:

  - The BSNL shall be the final judge of the quality of the work and the satisfaction of the BSNL in respect thereof set forth in the contract documents. Laxity of failure to enforce compliance with the contract documents by the BSNL and/or its representative shall not manifest a change or intent of waiver, the intention being that, not withstanding the same, the contractor shall be and remain responsible for complete and proper compliance with the contract documents and the specification therein. The representative of GMTD Solan has the right to prohibit the use of men and any tools, materials and equipment which in his opinion do not produce work or performance meet the requirement of the contract documents.

5.      TAXES AND DUTIES:

  - Contractor shall pay all rates, levies, fee royalties, taxes and duties payable or arising from out of, by virtue of or in connection with and/or incidental to the contract or any of the obligations of the parties in terms of the contractor documents and/or in respect of the works or operations or any part thereof to be performed by the contractor and he contractor shall indemnify and keep indemnified the BSNL from and against the same or any default by the contractor in the payment thereof.

6.      PROTECTION OF LIFE AND PROPERTY AND EXISTING FACILITIES:

  - The contractor is fully responsible for taking all possible safety precaution during preparation for and actual performance of the works and for keeping the construction site in a reasonable safe condition. The contractor shall protect all life and property from damage or losses resulting from his construction operations and shall minimize the disturbance and inconvenience to the public.

  - If the excavation of trench alters the contours of the ground around road and highway crossing in such locations dangerous to traffic, the contractor shall at his own cost, take all necessary precautions to protect public and shall comply with all the BSNL regulations as to placing of warning boards (minimum size 3’x2’), traffic signals, barricades, flags etc. at such location. If the contractor does not put the warning signal as per above directions, then a penalty of Rs. 500/- per day shall be levied on the contractor, till the directions are complied by the contractor. The contractor shall take due precautions to avoid damages to other pipe lines, water mains, sewers, telephones, telegraphs and power conduits, laid wires poles and guy wires, railways, highways, bridges or other underground or above ground structure and/or property crossing or adjacent to the cable trench being excavated.

    - Attention of the contractor is drawn to the rules regarding laying of cables at road crossing, along Railways Bridges, Highways safety precautions while working in public street. The contractor in writing shall obtain the detailed engineering instructions from the Divisional Engineer of the area.

  - The contractor shall be solely responsible for location through approved non-destructive means and ensuring the safety of all existing underground pipeline, electrical cables, and or other structures.

  - The contractor shall be solely liable for all expense for and in respect of repairs and/or damage occasioned by injury of or damage to such underground and above structures or other properties and under take to indemnify the BSNL from and against all actions, cause of actions, damages, claims and demands what-so-ever, either in law or in equity and all losses and damages and costs (inclusive between attorney and client), charges and expenses in connection therewith and/or incidental thereto. The contractor shall take all responsibilities and risk in crossing other pile lines and cables and shall be responsible for protecting all such existing pipelines, poles, electric lines, sewers, cables or other facilities from damage by the contractors operation in connection with the work. The contractor without cost of the BSNL shall promptly repair any damage incurred.

    - The current market value of any commodities lost a result of any damage to the aforesaid existing facilities shall be paid by the contractor together with such additional sums necessary to liquidate the personal of property damages, resulting there from.

7.      LABOUR WELFARE MEASURES AND WORKMAN COMPENSATION:

7.1	      Obtaining License before commencement of work:

(a)   The contractor shall obtain a valid labor license under the contract labor (R&A) Act 1970 and the contract labor (Regulation and Abolition) Central Rules 1971 before commencement of the work, and continue to have a valid license until the completion of work. The contractor shall also abide by the provisions of the Child Labor (prohibition and regulation) Act 1986. Any failure to fulfill this requirement shall attract the penal provisions of this contact arising out of the resultant non-execution of work.

(b)    Subject to the provisions of the Contract Labor (Abolition and Regulation Act, 1970) as amended from time to time, the contractor shall not commence actual work unless he produces a receipt from the concerned Licensing Authority that he has applied for licensing authority, which may be produced within the period of 15 days of commencing the work.

7.2	            CONTRACTORS LABOUR REGULATIONS:

    - Working hours

7.2.1.1.	Normally working hours of an employee should not exceed 9 hours a day. The working day shall be so arranged that inclusive of interval for rest, if any, it shall not spread over more than 12 hours on any day.

      - When a worker is made to work for more than 9 hours on any day or for more than 48 hours in any week he shall be paid over time for the extra hours put in by him.

      - Every worker shall be given a weekly holiday normally on a Sunday, in accordance with the provisions of Minimum Wages (Central) Rules 1960, as amended from time to time, irrespective of whether such worker is governed by the minimum wages act or not. Where the minimum wages prescribed by the Government, under the minimum wages act, are not inclusive of the wages for the weekly day of rest, the worker shall be entitled to rest day wages, at the rate applicable to the next preceding day, provided he has worked under the same contractor for a continuous period of not less than 6 days.

      - Where a contractor is permitted by the Engineer-in-charge to allow a worker to work on a normal weekly holiday, he shall grant a substituted holiday to him for the whole day, on one of the five days, immediately before or after the normal weekly holiday, and pay wages to such worker for the work performed on the normal weekly holiday at the overtime rate.

7.2.2.	Display of Notice Regarding Wages etc.

The contractor shall, before he commences his work on contract, display and correctly maintain and continue to display and correctly maintain, in a clear and legible condition in conspicuous places on the work, notices in English and in local Indian languages spoken by the majority of the workers, giving the minimum rates of the wages fixed under minimum wages act, the actual wages being paid, the hours of work for which such wage are earned, wages periods, dates of payments of wages and other relevant information.

    - Payment of wages

      - The contractor shall fix wage periods in respect of which wages shall be payable.

      - No wage period shall exceed one month.

7.2.3.3.            The wages of every person employed as contract labour in an

Establishment or by a contractor, where less than one thousand such persons are employed, shall be paid before the expiry of seventh day and in other cases before the expiry of tenth day after the last day of the wage period in respect of which the wages are payable.

      - Where the employment of any worker is terminated by or on behalf of the contractor, the wages earned by him shall be paid before the expiry of the second working day from the date on which his employment is terminated.

      - All payment of wages shall be made on a working day at the work

Premises and during the working time and on a date notified in advance and in case the work is completed before the expiry of the wage period, final payment shall be made within 48 hours of the last working day.

7.2.3.6.	Wages due to every worker shall be paid to him direct or to other person authorized by him in this behalf.

      - All wages shall be paid in current coin or currency or in both.

      - Wages shall be paid without any deductions of any kind except those specified by the Central government by general or special order in this behalf or permissible under the payment of wages act 1956.

      - A notice showing the wages period and the place and time of disbursement of wages shall be displayed at the place of work and a copy sent by the contractor to the Engineer-in-charge under acknowledgement.

      - It shall be the duty of the contractor to ensure the disbursement of wages in presence of the site engineer or any other authorized representative of the engineer-in-charge who will be required to be present at the place and time of the disbursement of wages by the contractor to workmen.

7.2.3.11          The contractor shall obtain from the site engineer or any other authorized representative of the engineer-in-charge, as the case may be, a certificate under his signature at the end of the entries in the “Register of wages” or the “wage-cum-muster roll”, as the case may be, in the following form:-

Certified that the amount shown in the column No………………………………… has been paid to the workman concerned in my presence on……………….. at………………..

7.2.4.		     Fines and deductions, which may be made from wages

      - The wages of a worker shall be paid to him without any deduction of any kind except the following:-

a)      Fines

b)     Deductions for absence from duty i.e. from the Place or the places   where by the terms of his Employment he is required to work. The amount of deduction shall be in proportion to the period for which he was absent.

c)     Deductions for damage to or loss of goods expressly entrusted to the employed person for custody, or for loss of money or any other deductions which he is required to account, where such damage or loss is directly attributable to his neglect or default.

d)    Deduction for recovery of advances or for adjustment of overpayment of wages,   advances granted shall be entered in a register.

e)    Any other deduction, which the central government may from time to time   allow.

      - No fines should be imposed on any worker save in respect of such acts and the Labour Commissioner has approved of omissions on his part as.

      - No fine shall be imposed on a worker and no deduction for damage or loss    shall be made from his wages until the worker has been given an opportunity of showing cause against such fines or deductions.

      - Every fine shall be deemed to have been imposed on the day of the act or omission in respect of which it was imposed.

7.2.5.	       Labor records

7.2.5.1.	            The contractor shall maintain a Register of Persons employed on work on contract in Form XIII of the Contract Labor(R&A) Central Rules 1971.

      - The contractor shall maintain a Muster Roll register in respect of all workmen employed by him on the work under contract in Form XIVI of the CL(R&A) Rules 1971.

      - The contractor shall maintain a Wage Register in respect of all workmen employed by him on the work under contract in Form XVII of the CL(R&A) Rules 1971.

      - Register of accidents:- The contractor shall maintain a register of accidents in such form as may be convenient at the work place but the same shall include the following particulars :

  - Full particulars of the laborers who met with accident.

  - Rate of wages

  - Sex

  - Age

  - Nature of accident and cause of accident

  - Time and date of accident

  - Date and time when admitted in hospital

  - Date of discharge from the hospital

  - Period of treatment and result of treatment

  - Percentage of loss of earning capacity and disability as assessed by Medical Officer

  - Claim required to be paid under workmen’s compensation act.

  - Date of payment of compensation.

  - Amount paid with details of the person to whom the same was paid.

  - Authority by whom the compensation was assessed

  - Remarks

      - The contractor shall maintain a Register of Fines in the Form XII of the CL(R&A) Rules 1971. The contractor shall display in a good condition and in a conspicuous place of work the approved list of acts and omission for which fines can be imposed.

      - The contractor shall maintain a Register of deductions for damage

Or loss in Form XX of the CL(R&A) Rules 1971.

      - The contractor shall maintain a Register of Advances in Form XXIII of the CL(R&A) Rules 1971.

    - The contractor shall maintain a Register of Overtime in Form XXIII of the CL(R&A) Rules 1971.

Attendance card-cum wage slip

      - The contractor shall issue an Attendance card cum wage slip to each workman employed by him.

      - The card shall be valid for each wage period.

      - The contractor shall mark the attendance of each workman on the card twice each day, once at the commencement of the day and again after the rest interval, before he actually tarts work.

      - The card shall remain in possession of the worker during the wage period under reference.

      - The contractor shall complete the wage slip portion on the reverse of the card at lease a day prior to the disbursement of wages in respect of the wage period under reference.

      - The contractor shall obtain the signature or thumb impression of the worker on the wage slip at the time of disbursement of wages and retain the card with him.

7.2.7               Employment card

The contractor shall issue an Employment Card in the Form XIV of CL (R&A) Central Rules 1971 to each worker within three days of the employment of the worker.

7.2.8.	           Service certificate

On termination of employment for any reason whatsoever the contractor shall issue to the workman whose services have been terminated, a service certificate in the Form XV of the CL(R&A) Central Rules 1971.

    - Preservation of labour records

The Labor records and records of fines and deductions shall be preserved in original for a period of three years from the date of last entries made in them and shall be made available for inspection by the Engineer-In-Charge or Labour Officer or any other officers authorized by the Ministry of Communication in this behalf.

  - Power of labor officer to make investigations or enquiry

The labor officer or any person authorized by the Central Government on their behalf shall have power to make enquiries with a view to ascertaining and enforcing due and proper observance of Fail Wage Clauses and provisions of these Regulations. He shall investigate into any complaint regarding the default made by the contractor in regard to such provision.

7.4		            Report of Investigating officer and action thereon

The Labor Officer or other persons authorized as aforesaid shall submit a report of result of his investigation or enquiry to the Engineer in-charge indicating the extent, if any, to which the default has been committed with a note that necessary deductions from the contractors bill be made and the wages and other dues be paid to the labourers concerned. The Engineer in-charge shall arrange payments to the labour concerned within 45 days from the receipt of the report from the Labor Officer or the authorized officer as the case may be.

7.5		             Inspection of Books And Slips

The contractor shall allow inspection of all the prescribed labor records to any of his workers or to his agent at a convenient time an place after due notice is received or to the Labor Officer or any other person, authorized by the Central Government on his behalf.

  - Submission of Returns

The contractor shall submit periodical return as may be specified from time to time.

  - Amendments

The Central Government may from time to time add to or amend the regulations and on any question as to be application/interpretation or effect of those regulations.

8.		           INSURANCE:

8.1	                 Without limiting any of his other obligations or liabilities, the contractor shall, at his own expense, take and keep comprehensive insurance including third party risk for the plant, machinery, men, materials etc. brought to the site and for all the work during the execution. The contractor shall also take out workmen’s compensations insurance as required by law and under take to indemnify and keep indemnified the BSNL from and against all manner of claims an demands and losses and damages and cost (including between attorney and client) charges and expenses that may arise in regard the same or that the BSNL may suffer or incur with respect to end/or incidental to the same. The contractor shall have to furnish originals and/or attested copies as required by the BSNL of the policies of insurance taken within 15 (fifteen) days of being called upon to do so together with all premium receipts and other papers related thereto which the BSNL may require.

9.	                  COMPLIANCE WITH LAWS AND REGULATION:

9.1  		During the performance of the works the contractor shall at his own cost and initiative fully comply with all applicable laws of the land and with any and all applicable by laws rules, regulations and orders and any other provisions having the force of law made or promulgated or deemed to be made or promulgated by the Government, Governmental agency or BSNL, municipal board, Government of other regulatory or authorized body or persons and shall provide all certificates of compliance therewith as may be required by such applicable law. By-laws, Rules, Regulations, orders and /or provisions. The contractor shall assume full responsibility for the payment of all contributions and pay roll taxes, as to its responsibility for the payment of all contributions and pay roll taxes, as to its employees, servants or agents engaged n the performance of the work specified in the contractor documents. If the contractor shall require

Any assignee or sub-contractor to sham any portion of the work to be performed hereunder may be assigned, sub-leased or sub-contracted to comply with the provisions of the clause and in this connection the contractor agrees as to undertake to save and hold the BSNL harmless and indemnified from and against any/all penalties, actions, suits, losses and damages, claims and demands and costs (inclusive between attorney and client) charges and expenses whatsoever arising out or occasioned, indirectly or directly, by failure of the contractor or any assignee or sub-contractor to make full and proper compliance with the said by-laws , Rules, Regulations, Laws and Order and provisions as aforesaid.

10.	                   TOOLS AND PLANTS

The contractor shall provide at his own cost all tools, plants, appliances, implements, measuring instruments etc. required for proper execution of works. The contractor shall also supply without charge the requisite number of persons with the means and materials necessary for the purpose of setting out works, counting, weighing and assisting the measurements for examination at any time and from time to time. The contractor shall be responsible to make all arrangements, at his own cost for dewatering of trenches/ducts and de-gasification of the ducts before carrying out the work. The contractor shall also be responsible to make arrangements, at his own cost, for water required for carrying of works at sites including curing of CC/RCC works. Failing his so doing the same may be provided by the Engineer-in-charge at the expense of the contractor and the expenses shall be deducted from any money due to the contractor under this contract or otherwise.

SECTION-VII

PARTICIPATION OF NEAR RELATIVES OF THE BSNL EMPLOYEE IN THE TENDER /EXECUTION OF WORKS IN BSNL UNITS

As per BSNL OBC & M Cell ND letter No. 151 08/2002-O & m/38 Dated 11-09-2002  the near relatives of BSNL employees either directly recruited or on deputation are prohibited from participation in Tender and execution of works in the different units of BSNL. The details guide lines in this regard are given in the following paragraphs.

- The near relatives for this purpose are defined as :

  - Members of a Hindu Undivided family,

  - They are husband and wife,

  - The one is related to the other in the manner as father, mother, son (s) son’s wife (daughter-in law), daughter (s) & daughter’s husband (son-in-law), brother (s) & brother’s wife, sister (s) & sister’s husband (brother-in-law)

- The Company or Firm or any other person is not permitted to apply Tender for works in any BSNL unit in which his/her near relative (s) is (are) posted. The unit is defined as SSA/Circle/Chief Engineer/ Chief Arch / Corporate office for non executive employees and all SSA in a circle including circle office/ Chief Arch. /Corporate Office for executive employees (including those called as Gazetted Officers /Executives at present). Therefore, it has been decided by the competent authority that while submitting the Tender, the Tenderer should give a certificate that none of his/her such near relative is working in the units as defined above where he /she is going to apply for Tender/ works. In case of proprietorship Firm, certificate will be given by the proprietor for partnership Firm certificate will be given by all the partners and in case of limited Company by all the Directors of the Company. Any breach of these conditions by the Company or Firm or any other person, the Tender/works will be cancelled and Earnest money/Security deposit will be forfeited at any stage whenever it is so noticed. The Company or Firm or the person will also be debarred for further participation in the concerned unit.

CERTIFCATE TO BE GIVEN BY TENDERER

I…………………………………….S/o…………………………………….R/o…………………………. hereby certify that none of my relative (s) as defined in the Tender document is/ are employed in any BSNL unit as per details given in Tender document. In case at any stage, it is found that the information given by me is false/incorrect, BSNL shall have the absolute right to take any action as deemed fit / without any prior intimation to me.

Signature of the Tenderer

Capacity in which Signed

SECTION - VIII

SCOPE OF WORK AND JURISDICTION OF CONTRACT

- SCOPE OF WORK

  - The optical fibre cable is to be laid through PLB pipes buried at a nominal depth of 165 cms. The steps involved in of cable construction are as under:

i)	Excavation of trench up to a nominal depth of 165cms. according to construction specifications along National /State Highways /other roads and also in city limits as mentioned in the notice inviting Tender.

ii)  Laying of PLB  Pipes/coils coupled by PLB sockets in excavated trenches , on bridges and culverts, drawing of 6 mm polypropylene para pro rope ( P.P . rope) through the PLB  pipes /coils as per Construction Specifications and sealing of PLB pipe ends at every manhole by PLB end caps of suitable size

iii) Providing of mechanical protection by RCC pipes /GI pipes and/or concreting /chambering according to construction specification, wherever required

iv)	Fixing of G.I. Pipes / Troughs with clamps at culverts / bridges and / or chambering or concreting of G.I. pipes / troughs, wherever necessary.

v)	Back filing and dressing of the excavated trenches according to construction specifications.

vi)	Opening of manholes ( of size 3 meters x1 meters x 1.65 meters depth),replacing existing 6 mm pp. ropes (form manhole to  manhole ) for ensuring smoothes passage for  pulling the cable , Pulling of optical fibre cable with proper tools and accessories as per construction specifications Sealing of both ends of the manholes by hard rubber bush of suitable size to avoid entry of rodents into the PLB pipes , putting split PLB pipes and split RCC pipes with proper  fixture over cable in the manhole to protect the bare cable in the pulling manhole, Back filling and dressing of manholes.

vii)	Digging of pit of size 2 meter x2 meter x 1.8 meter (depth) for construction of jointing chambers at approximately every two kilometers of internal size of 1.5 meter x 1.5 meter x 1.2 meter using bricks and mortar or fixing pre cast jointing chamber of internal diameter of 1.2 meter filling of jointing chamber with clean sand, placing either pre cast RCC cover   or stone of suitable size on jointing chamber to protect the joint and back filling of jointing chamber with excavated soil.

viii) Digging of pits 1 meter towards jungle side at every manhole and jointing chamber to depth of 60 cms. fixing of route indicator / joint indicator , concreting and back filling of pits , Painting of route indicator with yellow colour and joint indicator  red colour and sin writing denoting route /. Joint indicator number, as per construction specifications

ix)	Documentation.

1.2 	ALLIED ACTIVITIES:

    - Transportation of materials: The materials required for executing the work entrusted to the contractors against a work order shall be made available at District Store Depot at Solan.  In some cases the materials may be available at sub divisional store go down , The contractor shall be responsible for transporting the  materials, to be supplied by the BSNL or otherwise to execute the work under the contract, to site at his / their own cost.

1.2.2	Disposal of Empty Cable Drums:	The contractor shall be responsible to dispose of the empty cable drums after laying of the cables , the cost of various sizes of empty cable drums recoverable from the contractor has been fixed taking into account the prevailing market rates as mentioned in this document.

      - It shall be obligatory on part of the contractor to dispose of the empty cable drums at his/their level and the amount fixed for various empty cable drums shall be recovered from the bill for the work for which the drum(s) was/were issued or from and other amount due to the contractor or the Security Deposit.

      - The contractor shall not be allowed to dump the empty cable drums in Govt. /Public place which may cause inconvenience to the BSNL /public.  If the contractor does not dispose of the  empty cable drums within 3 days of becoming empty, the   BSNL shall be at liberty to dispose of the drums in any   manner deemed fit and also recover the amount fixed in this  contract from the bill/security deposit/any other amount due to  the contractor.

1.2.3	Supply of Materials:   There are some materials required to be supplied by the contractor for execution of the works under this contract like Bricks, Cement, Wire Mesh and steel for protection, etc., besides using other consumables which do/don’t become the part of the asset.  The contractor shall ensure that the materials supplied are of best quality and workmanship and shall be strictly in accordance with the specifications.

- COST OF WORK:  The estimated cost of work is as mentioned in the Notice Inviting Tenders in this Tender document. The actual value of work may vary based on the actual requirement but generally being limited to ± 25% of the indicated value.

Section – IX

Optical Fiber Cable Construction Specifications

OPTICAL FIBER CABLE CONSTRUCTION PRACTICES

The guidelines in the form of Engineering Instructions (E.Is.) on Construction Practices of Optical Fiber Cables are issued by T & D Circle of BSNL. The present practices are summarized here from the point of view of describing scope of work under various items of work.

Planning of OF Cable Route:-

6.1 	The Optical Fibre Cable route is planned considering the following objectives.

a) 	Minimum possible route length vis-à-vis route having maximum number of towns with potential telecom growth.

b) 	Linking of small exchanges off main road by leading in O.F.C. vis-a vis routing the main cable itself via such exchanges.

6.1.1 	After deciding above issues, a detailed measurement of lengths of cable route along with details of rail/road crossings, culverts, causeways, etc. is recorded in the detailed survey register. The probable locations of joints, terminations and regenerators is also decided and marked on the route map.

6.1.2 	On the basis of surveys, general permission from road and rail authorities for laying the Optical Fibre Cable along the decided routes and permission for rail / road crossings will have to be obtained. Generally, O.F.C. is laid straight as far as possible along the road near the boundaries, away from the burrow pits. The O.F.C. is laid along the roads at a minimum distance of 15 meters from the centerline of the road or in accordance with the permission from the concerned road authorities in view of their road-widening plan. As the O.F.C. carries high capacity traffic and is planned for 40 years of life, it is imperative that the cable is laid after obtaining due permission from all the concerned authorities to avoid any damage to the cable and/ or demand for its shifting at a later stage. This may result in disruption of services & thereby revenue loss.

6.1.3 	In special cases, where it may be necessary to avoid burrow pits or low lying areas, the cable may be run underneath the shoulder of the road at a distance of 0.6 meter from the outer edge of the road embankment provided the same is located at least 4.5 meters away from center line of road and 1.2 meter below the road surface.

6.1.4 	The Optical Fibre Cable is laid through PLB Pipes buried at a nominal depth of 165 cms.

6.1.5 	The work of laying of OF Cable in PLB pipe coil underground duct involves following activities.

a) 	Excavation of trench up to a nominal depth of 165 cms. Along National/ State Highways/ other roads including in city limits.

b) 	Laying of PLB pipe coils coupled by sockets in excavated trenches, on bridges and culverts, drawing of 6 mm polypropylene rope (P.P. rope)

c) 	Through the PLB pipe coils and sealing of PLB pipe ends at every manhole by end caps of suitable size.

d) 	Providing of mechanical protection by R.C.C. Pipes/ GI pipes and/or concreting/ chambering, wherever required.

e) 	Fixing of GI pipes/ troughs with clamps at culverts/ bridges and/or chambering or concreting of G.I. Pipes/ troughs, wherever necessary.

f) 	Back filling and dressing of the excavated trenches.

g) 	Opening of manholes (of size 3 meters x 1 meters x 1.65 meters depth), replacing existing 6 mm P.P. rope by 8 mm P.P. rope (from manhole to manhole) for ensuring smooth passage for pulling the cable. Pulling of Optical Fibre Cable with proper tools and accessories as per construction specifications. Sealing of both ends of the manholes by hard rubber bush of suitable size to avoid entry of rodents into the PLB pipes, putting split HDPE pipes and split RCC pipes with proper fixtures over cable in the manhole to protect the bare cable in the pulling manhole. Back filling and dressing of manholes.

h) 	Digging of pit of size 2 meter x 2 meter x 1.8 meter (depth) for construction of jointing chamber at approximately every two kilometers of internal size of 1.5 meter x 1.5 meter x 1.2 meter using bricks and mortar or fixing pre-cast jointing chamber of internal diameter of 1.2 meter filling of jointing chamber with clean sand, placing either pre-cast RCC cover or stone of suitable size on jointing chamber to protect the joint and back filling of jointing chamber with excavated soil.

i) 	Digging of pits 1 meter towards jungle side at every manhole and jointing chamber to a depth of 60 cms., fixing of route Indicator/joint indicator, concreting and back filling of pits. Painting of route indicators with yellow colour and joint Indicator by red colour and sign writing denoting route/joint indicator number, as per construction specifications.

6.2. 	Materials used for OF Cable work & their Specifications:

6.2.1 	PLB HDPE PIPE COILS The Optical Fibre Cable is pulled through 40 mm outer diameter Pipe Coils. Of either 1 Km. or 200 meters coil, should meet the specifications as given in GR no. G/CDS-OS/01 Dated December 1994 and revised up to date.

6.2.2 	PP Rope 6 mm PP rope is drawn through the PLB pipe coils and safely tied to the end caps at either ends with hooks to facilitate pulling of the OF cables at a later stage. The PP rope used is 3 strands Polypropylene Para Pro rope having yellow colour and shall be of 6 mm diameter and it should have a minimum breaking strength of 550 kgs. The length of each coil of rope should be 205 meters and it should conform to (i) BS 4928 Part-II of 1974 (ii) IS 5175 of 1982 (iii) It should be of special grade and should have ISI certificate mark (iv) It should be manufactured out of industrial quality Polypropylene.

6.2.3 	HDPE Socket For coupling PLB pipe coils, HDPE sockets as per IS 4984-1995 (O‘ ring type) made of High Density Polyethylene 5010 or equivalent injection grade material should be used. The HDPE sockets should be black in colour and should be fitted with hard rubber rings at both ends and should confirm to GR No. G/CDS-05/01 dated December, 1994 and revised up to date. 5mm x 5mm projections inside at a centre of the socket should be provided to prevent the pipes from passing through. It should weigh 150 gms. (With a tolerance of +/-5%) and should be able to withstand a pressure of 10 kg per sq. cms. without any damage/ deterioration in performance. (See figure ‘1’ for details)

6.2.4 	HDPE end caps For pulling the cable through the pipes, it is necessary to have suitable manholes at every 200M length and also at bends and corners suitably located. The pipes are laid for 200M or less at a time for the distance between two manholes. The ends of the HDPE/PLB pipe coils are closed with HDPE End Caps. The end caps used should be suitable for closing 50mm outer diameter class V HDPE/PLB pipes. The end cap should be manufactured from High Density Polyethylene, should withstand internal pressure of 10 kg per sq. cms., should be black in colour, should have a weight of 100 gms. (With a tolerance of +/-5%) and should conform to G/CDS-05/01 dated December, 1994 and revised up to date. (See figure ‘2’ for details). A suitable arrangement should be provided in the End Cap to tie PP Rope.

6.2.5 RUBBER BUSH To prevent entry of rodents into HDPE/PLB pipes, the ends of HDPE/PLB pipes are sealed at every manhole and joint using rodent resistant hard rubber bush (cap) after optical fibre cable is pulled. The rubber bush should be manufactured from hard rubber with grooves and holes to fit into 50 mm HDPE/PLB pipe (class V), so that it should be able to prevent the entry of insects, rodents, mud, and rainwater into the HDPE/PLB pipe. It should weight 150 gms (with a tolerance of +/- 5%. It should conform to specification No. G/CDS-05/01 dated December. 1994 and revised up to date. (Please see Figure No. 3).

6.2.6 MATERIALS FOR MECHANICAL PROTECTION For lesser depths requiring mechanical protection as per specifications and in built up areas, in towns and cities falling within the municipal limits, suitable mechanical protection is provided to HDPE/PLB pipes/coils using RCC full round/split RCC pipes or GI pipes or concreting of size 25 cms x 25 cms reinforced with MS weld mesh or a combination of any of these as per the written instructions of the Engineer-in-charge.

a) 	RCC FULL ROUND PIPES Reinforced cement concrete pipes (spun type) coupled with RCC collars sealed with cement mortar are used to provide mechanical protection to HDPE/PLB pipes/coils. The RCC pipes/collars should be of NP-2 class for 100 mm /150mm (internal diameter) full round, conforming to IS standard 458-1988 revised up to date. The pipes should have a nominal length of 2 meters. The RCC collars should be properly sealed using cement mortar 1:3 (1:53 grade cement of reputed brand, 3: fine sand without Impurities). If the mechanical protection is provided by RCC pipes, every third joint will be embedded in a concrete block of size 60 cms (L) x 40 cms (W) x 25 cms (H) of 1:2:4 cement concrete mix 1:2:4 (1: cement, 2: coarse sand, 4: stone aggregate of 20 mm nominal size) so that the alignment of RCC pipes remain firm and intact. Both ends of RCC / GI pipes will be sealed by providing concrete block of size 40 cm (L) x 40 cm (W) x 25 cm (H) of 1:2:4 cement concrete mix to avoid entry of rodents.

b) 	RCC FULL SPLIT PIPES Reinforced cement concrete pipes (spun type) with in-built collars are used to provide mechanical protection to HDPE/PLB pipes/coils. The RCC pipes should be of 100mm internal dia.(Spigotted), Class—NP-3, Thickness: 25mm, Length: 2 Meters with inbuilt collar at one end, Conforming to ISI Specification IS: 458, 1988 with latest amendment

c) 	G.I. PIPES G.I. pipes should be of medium duty class having diameter of 65 mm./40mm. The G.I. Pipes should conform to IS 554/1985 (revised up to date) IS 1989 (Part-I), 1900 Sockets (revised up to date) & IS 1239 (Part-II) 1992 (revised up to date). Wherever protection by G.I. pipe is provided, it is preferable to use HDPE coils. As space on parapet wall on Bridges/culverts is limited, 40 mm GI pipes may be used with 32 mm HDPE coil drawn inside.

d) 	M.S. WELD MESH:  The HDPE/PLB pipes can also be protected by embedding it in concrete of size of 25 cms x 25 cms reinforced with MS weld mesh. The MS weld mesh used should be of 50 mm x 100 mm size, 12 SWG, 120 cms in width in rolls of 50m each. One meter of MS weld mesh caters to approx. 3 meters of concreting. (See figure ‗3‘for details) The strength of RCC/CC is dependent on proper curing; therefore, it is imperative that water content of CC/RCC mix does not drain out into the surrounding soil. In order to ensure this, the RCC/cc work should be carried out by covering all the sides by yellow PVC sheets of weight not less than 1 kg per 8 sq.m. to avoid seepage of water into the soil.

6.2.7 	JOINT CHAMBER The joint chamber is provided at every joint normally at a distance of 2 kms to keep the O.F.C. joint well protected and also to keep extra length of cable which may be required in the event of faults at a later date. The joint chambers are made at site using bricks and mortar or are of pre-cast RCC type.

a) 	Construction of brick chamber at site: - For constructing brick chamber, first a pit of size 2m x2 mx1.8 m depth is required to be dug. Then, base of the chamber is made using concrete mix of 1:5:10 (1: cement, 5: coarse sand, 10: graded stone aggregate 40mm nominal size) of size of 1.7m x 1.7 m x 0.15 m (thickness). Wall of brick chamber having internal dimensions of 1.2 m x 1.2 m x 1 m (H) should be constructed on this base having wall thickness of 9” using cement mortar mix of 1:5 (1: cement, 5: fine sand). The bricks to be used for this purpose should be of size 9” x 4.5” x 3”, best quality available and should have smooth rectangular shape with sharp corners and shall be uniform in colour and emit clear ringing sound when struck. The joint chamber should be so constructed that HDPE/PLB pipe ends remain protruding minimum 5cms inside the chamber on completion of plastering. The HDPE/PLB pipes should be embedded in wall in such a way so that, the bottom brick should support the pipe and upper brick should be provided in a manner that HDPE/PLB pipe remains free from the weight of the construction. The joint chamber should be plastered on all internal surfaces and top edges with cement mortar of 1:3 (1: cement, 3: coarse sand), 12 mm thick finished with a floating coat of complete cement as per standard. Pre-cast RCC slab with two handles to facilitate easy lifting, of size 0.7 m x 1.4 m and of thickness of 5 cm having one handle for each half in centre and word ‗‘OFC‘ engraved on it are to be used to cover the joint chamber. Two numbers of such slabs are required for one joint chamber. This pre-cast slab should be made of cement concrete mix of 1:2:4 (1: cement, 2: coarse sand, 4: stone aggregate 6 mm nominal size) reinforced with steel wire fabric 75 x 25 mm mesh of weight not less than 7.75 Kg per sq. meter. The joint chamber is filled with clean sand before closing. Lastly, back filling of joint chamber pit with excavated soil is carried out.

b) 	Pre cast RCC chamber For fixing pre cast RCC chamber, first a pit of size 2 m x 2 m x 1.8 m depth is required to be dug. Pre cast RCC chamber consists of three parts (I) round base plate in two half of 140 cm dia and 5 cm thickness (ii) full round RCC joint chamber with dia of 120 cm and height of 100 cm and thickness of 5 cm (iii) round top cover will be in two halves with dia of 140 cm and thickness of 5 cm having one handle for each half in centre and word “OFC‘ engraved on it. (See figure ‘5’). After, fixing the pre cast RCC joint chamber, the joint chamber is filled with clean sand before closing. Lastly, back filling of joint chamber pit with excavated soil is carried out.

6.2.8 	ROUTE/ JOINT INDICATOR: - The route/joint indicators are co-located with each manhole/joint chamber. In addition route indicators are also to be placed where route changes direction like road crossings etc. The route /joint indicator made of pre-cast RCC should have the following dimensions:

Base - 250 mm x 150 mm

Top - 200 mm x 75 mm

Height - 1250 mm

The word ‘BSNL OFC’ should be engraved on the route/ joint indicators. (See figure ‘6’ for details) The route indicators are painted yellow and the same are placed at 2 ft. away from the centre of the trench towards jungle side. The joint indicators are placed at OFC joints and placed 1 ft. away from wall of the joint chamber facing jungle side and are painted red. The engraved word BSNL OFC” should be painted in white, on route as well as joint indicators. Numbering of route indicators/joint indicators should also be done in white paint. The numbering scheme for route indicators will be Joint No./Route Indicator No. for that joint. For example, 2/6 marking on a route indicator means 6th route indicator after 2nd joint. Additional joints on account of faults at a later date should be given number of preceding joint with suffix A, B, C, and D. For example sign writing 2A on a joint indicator means, additional joint between joint No. 2 and 3. The numbering of existing route/joint indicator should not be disturbed on account of additional joints. Enamel paints of reputed brand should be used for painting and sign writing of route as well joint indicators.

6.3. 	EXACAVATION OF TRENCHES: -

6.3.1 	Trenching

Location and Alignment of the Trench: In city areas, the trench will normally follow the foot-path of the road except where it may have to come to the edge of the carriage way cutting across road with specific permissions from the concerned authorities maintaining the road (such permissions shall be obtained by the department). Outside the city limits the trench will normally follow the boundary of the roadside land. However, where the road side land is full of burrow pits or forestation or when the cable has to cross culverts/ bridges or streams, the trench may come closer to the road edge or in some cases, over the embankment or shoulder of the Road (permissions for such deviations for cutting the embankment as well as shoulder of the road shall be obtained by the department). The alignment of the trench will be decided by a responsible departmental official, not below the rank of a Junior Telecom Officer. Once the alignment is marked, no deviation from the alignment is permissible except with the approval of Engineer-in- charge. While marking the alignment only the centre line will be marked and the Contractor shall set out all other work to ensure that, the excavated trench is as straight as possible. The Contractor shall provide all necessary assistance and labour, at his own cost for marking the alignment. Contractor shall remove all bushes, undergrowth, stumps, rocks and other obstacles to facilitate marking the centre line without any extra charges. It is to be ensured that minimum amount of bushes and shrubs shall be removed to clear the way and the contractor shall give all, consideration to the preservation of the trees. The line up of the trench must be such that HDPE Pipe(s) shall be laid in a straight line, both laterally as well as vertically except at locations where it has to necessarily take a bend because of change in the a alignment or gradient of the trench, subject to the restrictions mentioned else where.

6.3.2 	Line-Up: The line-up of the trench must be such that HDPE/PLB pipe(s) shall be laid in a straight line except at locations where it has to necessarily take a bend because of change in the alignment or gradient of the trench, subject to the restrictions mentioned elsewhere.

6.3.3 	Method of Excavation: In city limits as well as in built up areas, the contractor shall resort to use of manual labour only to ensure no damage is caused to any underground or surface installations belonging to other public utility services and/or private parties. However, along the Highways and cross country there shall be no objection to the Contractor resorting to mechanical means of excavation, provided that no underground installations exist in the path of excavation, if any, are damaged.

There shall be no objection to resort to horizontal boring to bore a hole of required size and to push through G.I. Pipe (65 mm/ 40mm dia) through horizontal bore at road crossing or rail crossing or small hillocks etc.

All excavation operations shall include excavation and ‗getting out‘. ‗Getting out‘ shall include throwing the excavated materials at a distance of at least one meter or half the depth of excavation, whichever is more, clear off the edge of excavation. In all other cases getting out’ shall include depositing the excavated materials as specified.

In Rocky strata excavation shall be carried out by use of electro mechanical means like breakers or by blasting wherever permissible with express permission from the competent authority. If blasting operations are prohibited or not practicable, excavation in hard rock shall be done by chiseling.

Trenching shall as far as possible be kept ahead of the laying of pipes. Contractor shall exercise due care that the soil from trenching intended to be loose for back filling is not mixed with loose debris. While trenching, the Contractor should not cause damage to any underground installations belonging to other agencies and any damage caused should be made good at his own cost and expense.

Necessary barricades, night lamps, warning board and required watchman shall be provided by the contractor to prevent any accident to pedestrians or vehicles. While carrying out the blasting operations, the contractor shall ensure adequate safety by cautioning the vehicular and other traffic. The contractor shall employ sufficient man-power for this with caution boards, flags, sign writings etc.

The contractor should provide sufficient width at the trench at all such places, where it s likely to cave in due to soil conditions without any extra payment. A minimum free clearance of 15 cms should be maintained above or below any existing underground installation. No extra payment will be made towards this.

In order to prevent damage to HDPE/PLB pipes over a period of time, due to the growth of trees, roots, bushes, etc., the contractor shall cut them when encountered in the path of alignment of trench without any additional charges.

In large burrow pits, excavation may be required to be carried out for more than 165 cms in depth to keep gradient of bed less than 15 degrees with horizontal. If not possible as stated above, alignment of trench shall be changed to avoid burrow pit completely.

6.3.4 	Depth and Size of the Trench: The depth of the trench form top of the surface shall not be less than 165 cms unless otherwise relaxation is granted by competent authority under genuine circumstances. In rocky terrain, the depth of the trench may be restricted to a depth of 100 to 140 cms. However, Engineer-in- charge in exceptional cases due to adverse site conditions encountered, may allow to lay HDPE/PLB pipes at a lesser depth with additional protection. In all cases, the slope of the trench shall not be less than 15 degrees with the horizontal surface. The width of the trench shall normally be 45 cms. at the top & 30 cms. at the bottom. In case, additional pipes (HDPE/GI/RCC Pipes) are to be laid in some stretches, the same shall be accommodated in this normal size trench.

When trenches are excavated in slopes, uneven ground, inclined portion, and the lower edge shall be treated, as top surface of land and depth of trench will be measured accordingly. In certain locations, such as uneven ground, hilly areas and all other Places, due to any reason whatsoever it can be ordered to excavate beyond standard depth of 165 cms to keep the bed of the trench as smooth as possible. Near the culverts, both ends of the culverts shall be excavated more than 165 cms. to keep the gradient less than 15 degree with horizontal. For additional depth in excess of 165 cms., additional payment of pro rata basis shall be applicable. If excavation is not possible to the minimum depth of 165 cms., as detailed above, full facts shall be brought to the notice of the Engineer in charge in writing giving details of location and reason for not being able to excavate that particular portion to the minimum depth. Approval shall be granted by the competent authority in writing under genuine circumstances. The decision of the competent authority shall be final and binding on the contractor.

6.3.5 	Dewatering: The Contractor shall be responsible for all necessary arrangements to remove or pump out water from trench. The Contractor should survey the soil conditions encountered in the section and make his own assessment about dewatering arrangement that may be necessary. No extra payment shall be admissible for this.

6.3.6 	Wetting: Wherever the soil is hard due to dry weather conditions, if watering is to be done for wetting the soil to make it loose, the same shall be done by the contractor. No extra payment shall be admissible for this.

6.3.7 	Blasting: For excavation in hard rock, where blasting operations are considered necessary, the contractor shall obtain approval of the Engineer-in-Charge in writing for resorting to blasting operation. The contractor shall obtain license from the competent authority for undertaking blasting work as well as for obtaining and storing the explosive as per the Explosive Act, 1884 as amended up to date and the explosive Rules, 1983. The contractor shall purchase the explosives fuses, detonators, etc. only from a licensed dealer. Transportation and storage of explosive at site shall conform to the aforesaid Explosive Act and Explosive Rules. The contractor shall be responsible for the safe custody and proper accounting of the explosive materials. Fuses and detonators shall be stored separately and away from the explosives. The Engineer-in-Charge or his authorized representative shall have the right to check the contractor‘s store and account of explosives. The contractor shall provide necessary facilities for this. The contractor shall be responsible for any damage arising out of accident to workmen, public or property due to storage, transportation and use of explosive during blasting operation. Blasting operations shall be carried out under the supervision of a responsible authorized agent of the contractor (referred subsequently as agent only), during specified hours as approved in writing by the Engineer-in-Charge. The agent shall be conversant with the rules of blasting. All procedures and safety precautions for the use of explosives drilling and loading of explosives before and after shot firing and disposal of explosives shall be taken by the contractor as detailed in IS: 4081 safety code for blasting and related drilling operation.

6.3.8 	Trenching near Culverts/ Bridges: The HDPE/PLB pipes shall be laid in the bed of culvert at the depth not less than 165 cms protected by G.I. pipes and concreting as decided by Engineer- in charge. Both ends of culverts shall be excavated more than 165 cms in depth to keep the gradient of not less than 15 degree with horizontal. The bed of trench should be as smooth as possible. While carrying out the work on bridges and culverts, adequate arrangement for cautioning the traffic by way of caution boards during day time and danger lights at night shall be provided. In case of small bridges and culverts, where there is a likelihood of their subsequent expansion and remodeling, the cable should be laid with some curve on both sides of the culvert or the bridge to make some extra length available for readjustment of the cable at the time of reconstruction of culvert or the bridge.

6.4 	LAYING OF PLB HDPE PIPES: After the trench is excavated to the specified depth, the bottom of the trench has to be cleared of all stones or pieces of rock and leveled up properly. A layer of soft soil/ or sand (in case the excavated material contains sharp pieces of rock/ stones) of not less than 5 cms is required for leveling the trench to ensure that the cable when laid will follow a straight alignment. Adequate care shall be exercised while laying so that the OF cables are not put to undue tension/pressure after being laid as this may adversely affect the optical characteristics of cables with passage of time.

The contractor shall ensure that trenching and pipe laying activities are continuous, without leaving patches or portions incomplete in between. In case intermediate patches are left, measurement of the completed portions will be taken only after work in such left over patches are also completed in all respects.

Preparatory to aligning the pipe for jointing, each length of the HDPE/PLB pipe shall be thoroughly cleaned to remove all sand, dust or any other debris that may clog, disturb or damage the optical fibre cable when it is pulled at a later stage. The ends of each pipe and inside of each Socket shall be thoroughly cleaned of any dirt or other foreign materials.

After the trench is cleaned the HDPE/PLB pipes/Coil shall be laid in the cleaned trench, jointed with “O” ring type Sockets & 6mm PP rope should be drawn through the HDPE/PLB pipes at the time of laying the pipes to facilitate cable pulling at a later stage. At every manhole approximately at every 200m or at bends or turns the PP rope will be tied to the HDPE end caps used for sealing the HDPE/PLB pipes, to avoid entry of rodents/mud etc.

At the end of each day work, the open ends of the pipes sections shall be tightly closed with end caps to prevent the entry of dirt/mud, water or any foreign matter into HDPE/PLB pipes until the work is resumed.

In City, Town, Urban area falling within Municipal/Corporation limits, the HDPE/ LB pipes shall be laid with protection using RCC/G.I. Pipes/ Concreting reinforced with weld mesh. Moreover, in cross country routes, if depth is less than 1.2 meters, protection by using RCC/G.I. Pipe/ Concreting reinforce with weld mesh shall be provided. Engineer-in-Charges shall decide about such stretches and type of protection to be provided in view of the site requirements. Normally 100 mm RCC Pipes shall be used for protecting HDPE/PLB pipe but if more than one HDPE/PLB pipe is to be laid and protected, RCC Pipe of suitable size to accommodate the required number of HDPE Pipes shall be used.

The HDPE/PLB pipes shall be laid in RCC Full Round spun Pipes/GI Pipes as required at road crossings. The RCC pipes/GI pipes shall extend at least 3 meters on either side of the road at road crossings. At road crossings, extra GI/HDPE/PLB pipes may be laid as per the direction of the Engineer-in charge. On Rail bridges and crossings, the HDPE/PLB pipes shall be encased in suitable cast iron as prescribed by the Railway Authorities. Wherever RCC pipes are used for protection, the gaps between the RCC collars and the RCC pipes shall be sealed using cement mortar 1:3 (1:53 grade cement of reputed brand, 3: fine sand without impurities) to bar entry of rodents. Every third collar of RCC pipes (normally of 2 meters length) and also both ends of RCC Pipes will be embedded in a concrete block of size 40 cms (L)x 40 cms (W) x 25 cms (H) of 1:2:4 cement concrete mix (1:53 grade cement of reputed brand, 2: coarse sand, 3: stone aggregate of nominal size of 20 mm ) so that the alignment of RCC pipes remain firm and intact and to avoid entry of rodents.

Wherever GI pipes are used, special care should be taken to ensure that G.I. Pipes are coupled properly with the sockets so as to avoid damage to HDPE/PLB pipe and eventually the OF Cable in the event of pressure coming on the joint and G.I. Pipe joint giving its way. Rubber bushes shall be used at either ends of the GI pipes to protect HDPE/PLB pipe. Both the ends of G.I. Pipe will be embedded in a concrete block of size 40 cms (L) x 40 cms ((W) x 25 cms (H) of 1:2:4 cement concrete mix (1:53 grade cement of reputed brand, 2: coarse sand, 3: stone aggregate of nominal size of 20 mm) so that the alignment of G.I. Pipes remain firm and intact and to avoid entry of rodents.

In case of protection by concreting at site, the nominal dimension of concreting shall be 250 mm x 250 mm section. Cement Concrete Mixture used shall be of 1:2:4 composition i.e. 1:53 grade Cement of a reputed company , 2: Coarse Sand, 4: Graded Coarse Stone aggregate of 20 mm nominal size, reinforced with MS weld mesh. As the RCC is cast at site, it is imperative to ensure that special care is taken to see that proper curing arrangements are made with adequate supply of water. The contractor shall invariably use mechanical mixer at site for providing RCC protection, to ensure consistency of the mix.

For carrying out concreting work in trenches, yellow PVC sheets of width not less than 1.0 M and of weight not less than 1 kg. Per 8 sq. meters shall be spread and nailed on sides of the trench to form trapezoidal section for concreting in the cleaned trench, to avoid seepage of water into the soil. A bed of cement concrete mixture of appropriate width and 75 mm thickness shall be laid on the PVC sheet, before laying HDPE pipes. The HDPE/PLB pipes shall then be laid above this bed of concrete. After laying the HDPE/PLB pipes, MS weld mesh is wrapped around and tied and concrete mix is poured to form the cross sectional dimensions as instructed by the Engineer-in- charge. The strength of RCC is dependent on proper curing; therefore, it is imperative that water content of RCC mix does not drain out into the surrounding soil. Portions where cement concreting has been carried out shall be cured with sufficient amount of water for reasonable time to harden the surface. After curing, refilling of the balance depth of the trench has to be carried out with excavated soil. The HDPE/PLB pipes/RCC/GI Pipes shall be laid only in trenches accepted by Engineer-in-Charge or his representative. The Contractor shall exercise due care to ensure that the HDPE/PLB pipes are not subjected to any damage or strain.

Water present in the trench at the time of laying the HDPE/PLB pipes shall be pumped out by the contractor before laying the pipes in the trench to ensure that no mud or water gets into the pipes, thus choking it. In case of nallahs, which are dry for nine months in a year, the HDPE/PLB pipes shall be laid inside the RCC Pipes/ or GI Pipes and concrete laid at a minimum depth of 165 cms., as instructed by the Engineer-in-charge. The mechanical protection shall extend at least 5 meters beyond the bed of nallah on either side. Not with standing anything contained in clauses referred above, the Engineer-in-charge may order, based on special site requirements, that the HDPE Pipes may be encased in reinforced cement concrete, as detailed, ibid. While laying the pipes, a gap of 2 M is kept at convenient locations approx. 200 m apart and at the bends and turns, which will be used as manholes during OF cable pulling. Ends of the HDPE/PLB pipes at the manholes shall be sealed using end caps after tying the PP rope to the end caps to avoid choking of the pipes. In a similar manner, manholes shall be kept while approaching bridges, road crossings etc., as instructed by the Engineer-in-charge. The location of the manholes will be decided by the Engineer-in-charge.

6.4.1 	Laying Protection Pipes on Bridges and Culverts: In case trenching and pipe laying is not possible in the beds of the culverts, the pipes shall be laid over the culverts/bridges after getting due permission from the competent authority. Of late the bridge construction authorities are providing ducts below the footpaths on the bridges for various services. The telecom officers need to maintain good liaison with the concerned authority to get one side of the duct allotted for Telecom Cables. In such ducts, G.I. Pipes can be coupled and laid for pulling the cables. It would be pertinent to mention here that close liaison with bridge construction authorities would be of immense advantage in ensuring provision of ducts on one or both the sides of the bridges as per future requirements. However, for laying cables on existing bridges, where duct arrangement does not exist, one of the following methods may be adopted.

Normally in the Bridges/ Culverts, where there are no ducts and where the cushion on the top of the Arch is 50 cm to 100 cm or more, G.I. Pipe (Carrying HDPE/PLB pipe and cable) may be buried on the top of the Arch adjoining the parapet wall, by digging close to the wheel guards. Every precaution shall be taken to see that no damage occurs to the arch of the culvert. After burying the GI pipe, the excavated surface on the arch shall be restored.

Where the thickness of the Arch is less than 50 cms, the pipe must be buried under the wheel guard masonry and the wheel guard rebuilt.

If neither of the two methods is possible, the G.I. Pipes/GI Troughs must be clamped outside the parapet wall with the clamps supplied by the department. If necessary, the pipes may be taken through the parapet wall at the ends where the wall diverges away from the road.

In case where the methods explained in clauses referred above are not possible, the G.I. Pipe/GI Troughs can be fixed on the top of the road kerb close to the inside face of the parapet wall by means of clamps supplied, using raw plugs and wood screws or small diameter bolts, without damaging the concrete and limiting the external diameter of the bolts to 7.5 mm. The permission for carrying out this work will be obtained from the Road Authorities by the department.

Methods cited in above clauses should be carried out under close supervision of Road authorities.

The surface to be concreted should be thoroughly cleaned and leveled before concreting. At both ends of the Bridges/Culverts, where the GI Pipes /GI Troughs slope down and get buried, the concreting should be extended to ensure that no portion of the GI Pipes/GI Troughs is exposed as ordered by the Engineer- in- charge to protect the pipe/Trough from any possible damage externally caused.

Where white wash/ colour wash is existing on the Bridges/ Culverts, the same should also be carried out on the concreted portion to ensure uniformity.

6.5 	Back Filling and Dressing of the Trench: The earth used for filling shall be free from all roots, Grass, shrubs, vegetation, trees, saplings and rubbish. Provided that the HDPE/PLB pipes have been properly laid in the trench at the specified depth, the back filling operation shall follow as closely as practicable. The back filling operation shall be performed in such a manner so as to provide firm support under and above the pipes and to avoid bend or deformation of the HDPE/PLB pipes when the pipes get loaded with the back filled earth. At locations where the back filled materials contains stones/sharp objects which may cause injury to the HDPE/PLB pipes and where the excavated or rock fragments are intended to refill the trench in whole or in part, the trench should be initially filled, with a layer of ordinary solid or de-rocked loose earth of not less than 10 cms above the pipes. Back filling on public, private roads, railway crossings, footpaths in city areas shall be performed immediately after laying the HDPE pipes. Back filling at such locations shall be thoroughly rammed, so as to ensure original condition and made safe for traffic. All excess soil/ material left out on road/ footpath/railway crossing shall be removed by contractor. However, along the high way and cross-country, the dug up material left out should be kept as heap above the trench while refilling. In city limits, no part of the trench should be kept open for more than 50 meter length at any time and in all places where excavation has been done, no part of the trench should be kept open over night to prevent any mishap or accident in darkness.

6.6 	CABLE PULLING AND JOINING/ SPLICING: -

6.6.1 	CABLE PULLING : Manholes marked during HDPE/PLB pipe laying of approx. size of 3m length x 1.0 m. width x 1.65 m. Depth shall be excavated for pulling the cables. There may be situations where additional manholes are required to be excavated, for some reasons, to facilitate smooth pulling of cable. Excavation of additional manholes will be carried out, without any extra cost. De-watering of the manholes, if required, will be carried out without any extra costs. De-watering/De-gasification of the ducts, if required, will be carried out without any extra costs.

The existing 6mm PP rope shall be replaced by with PP rope of 8 mm dia between the two consecutive manholes. This is to ensure that the HDPE/PLB pipes are cleaned for pulling the cable without exerting undue tension on the OF cable. While cleaning, excessive pressure should not be put which may result in breaking of PP rope and thus require opening of additional manholes. However, in case the cleaning rope gets stuck up during pulling, the location of clogging of HDPE/PLB pipe should be measured and located accurately. The trench at that location should be opened and the HDPE/PLB pipe should be cleaned properly or if not possible it should be changed by a clean new HDPE Pipe to facilitate easy cable pulling at a later stage without any breakage. If clogging of HDPE/PLB pipe is in the location where the pipes are protected either by RCC Pipe or by concreting and the protection is broken for cleaning/changing the HDPE/PLB pipe, the protection thus removed should be brought back to normal by the contractor without any extra cost. However, HDPE Pipes, RCC Pipes required for this purpose will be supplied by the Department.

The Optical fibre cables are available in drums in lengths of appox. 2Kms. The cables shall be manually pulled through already laid HDPE/PLB pipes by using the 8 mm PP rope. This work is to be carried out under the strict supervision of site in-charge. At a time, maximum three persons at every manhole should be deployed to pull the cable as more tension to cable may lead to breaking of fibers. Cost of such damages will be recovered from the contractor.

After pulling of the drum is completed, both ends of the HDPE/PLB pipe in each manhole should be sealed by hard rodent resistant rubber bush, to avoid entry of rodents/mud into HDPE/PLB pipes.

The Manholes are prepared by providing 65mm split HDPE/PLB pipe of 2.5 to 3m length and closing the split HDPE/PLB pipes by providing necessary clamps/ adhesive tape as per the directions of Engineer-in- charge. Afterwards, the split/cut HDPE/PLB pipe are covered with 100 mm split RCC pipe of 2m length and sealing the ends of RCC pipe with lean cement solution for protecting bare cable in the manhole . After fixing of HDPE/RCC Split Pipes necessary back filling/reinstatement and dressing of manholes should be carried out as referred under trenching. The location of the pulling manhole should be recorded for preparation of documentation.

6.6.2 	Jointing/ Splicing : The OFC cable drums are usually of 2 Kms in length hence optical fibre joints will be approx. at every 2 Kms. The 6/12/24 fibers are to be spliced at every 2 Kms. & at both ends (Terminations) in the equipment room as directed by the Engineer-in-charge. The Infrastructure required for cable splicing i.e.: -

- Splicing machine

- Air Conditioned Van

- OTDR

- Optical tool set

- Tool kit etc.

Will be arranged by the bidder at his own cost and also any additional accessories e.g. engine etc. required at site for splicing will also be arranged by the bidder at his own cost. The optical fibre cable thus jointed end-to-end will be tested by an officer of A/T unit for splice losses and transmission parameters as specified by TCHQ and prevalent at that time. The OF cable should meet all the parameters, specified and no relaxation will be granted. It should also be ensured that during jointing no fibers are interchanged or broken. The number of joints should not be more than 10 % of the theoretical value calculated by the department.

6.7 	Construction of Jointing Chamber: - The joint chambers are provided at every joint to keep the O.F.C. joint well protected and also to keep extra length of cable, which may be, required to attend the faults at a later date. Jointing chambers are to be prepared normally at a distance of every 2 kms. Actual location of jointing chamber depends on length of cable drum and appropriateness of location for carrying out jointing work. The location is finalized by Engineer-in-charge. The jointing chambers are constructed either of brick masonry work at site & pre cast RCC slabs for covers or by way of fixing pre-cast RCC chambers and covers as per the instructions from Engineer-in- charge.

6.7.1 	Construction of brick chamber at site: For constructing brick chamber, first a pit of size 2 m x 2 m x1.8m depth is required to be dug. Then, base of the chamber is made using concrete mix of 1:5:10 (1: cement, 5: coarse sand, 10: graded stone aggregate 40 mm nominal size) of size of 1.7 m x 1.7 m x 0.15 m (thickness). Walls of brick chamber having internal dimensions of 1.2 m x 1.2 m x1 m (H) should be constructed on this base having wall thickness of 9” using cement mortar mix of 1:5 (1: cement, 5: fine sand). The bricks to be used for this purpose should be of size 9” x 4.5” x3”, best quality available and should have smooth rectangular shape with sharp corners and shall be uniform in colour and emit clear ringing sound when struck. The joint chamber should be so constructed that HDPE pipe ends remain protruding minimum 5 cms inside the chamber on completion of plastering. The HDPE/PLB pipes should be embedded in wall in such a way so that, the bottom brick should support the pipe and upper brick should be provided in a manner that HDPE pipe remains free from the weight of the construction. The joint chamber should be plastered on all internal surfaces and top edges with cement mortar of 1:3 (1: cement, 3 coarse sand) 12 mm thick finished with a floating coat of complete cement as per standard. Pre-cast RCC slab with two handles to facilitate easy lifting, of size 0.7 m x 1.4 m and of thickness of 5 cm having one handle for each half in centre and word OFC‘ engraved on it are to be used to cover the joint chamber. Two numbers of such slabs are required for one joint chamber. This pre-cast, slab should be made of cement concrete mix of 1:2:4 (1: cement, 2: coarse sand, 4 stone aggregate 6 mm nominal size) reinforced with steel wire fabric 75 x 25 mm of weight not less than 7.75 Kg per sq. meter The joint chamber is filled with clean sand before closing. Lastly, back filling of joint chamber pit with excavated soil should be carried out up to normal ground level and compacted.

6.7.2 	Pre cast RCC chamber : For fixing pre cast RCC chamber, first a pit of size 2 m x 2m x 1.8 m depth is required to be dug. Pre cast RCC chamber consists of three parts (i) round base plate in two half of 140 cm dia and 5 cm thickness (ii) full round RCC joint chamber with dia of 120 cm and height of 100 cm and thickness of 5 cm (iii) round top cover will be in two halves with dia of 140 cm and thickness of 5 cm having one handle for each half in centre and word “OFC‘engraved on it. (See figure ‘4’) Pre cast RCC chamber (which is coming in part) should be placed in the pit and parts should be fixed by applying cement mortar. The pre cast RCC chamber will be supplied by the department. After, fixing the pre cast RCC joint chamber, the joint chamber is filled with clean sand before closing. Lastly, back filling of joint chamber pit with excavated soil should be carried out up to normal ground level and compacted.

The work of cable pulling includes the work of cable pulling up to exchange termination point and has to be carried out as per the directions of Engineer-in-charge.

6.8 	Fixing of Route Indicators/ Joint Indicators: Pits shall be dug 1 M. towards jungle side at every manhole and jointing chamber for fixing of Route/Joint Indicator. In addition, Route Indicators are also required to be placed where O.F. Cable changes directions like road crossing etc. The pits for fixing the indicator shall be dug for a size of 60 cms. x 60 cms. and 75 cms. (Depth). The indicator shall be secured in upright position by ramming with stone and murrum up to a depth of 60 cms. and concreting in the ratio of 1:2:4 (1: cement, 2: coarse sand, 4 stone aggregate 20 mm nominal size) for the remaining portion of 15 cms. Necessary curing shall be carried out for the concreted structure with sufficient amount of water for reasonable time to harden the structure. The route and joint indicator shall be painted with primer before painting with oil paint. The material used should bear ISI mark. The size of each written letter should be at least 3.5 cms. The colors of painting and sign writing are as under: -

a) For Joint Indicator Red.

b) For Route Indicator Yellow.

c) For Letters White.

The numbering scheme for route indicators will be Joint No./Route Indicators No. for that joint. For example 2/6 indicator means 6th route indicator after 2nd joint. Additional joints on account of faults at a later date should be given number of preceding joint with suffix A, B, C and D. For example sign writing 2A on a joint indicator means, additional joint between Joint No. 2 and 3. The numbering existing route/ joint indicator should not be disturbed on account of additional joints.

6.9 	Documentation: The documentation, consisting of the following shall be prepared exchange to exchange for Intra SSA OFC links and for each section in case of inter SSA/National Long distance routes.

a) 	L-14 Diagrams – General: - This diagram shall consist of Cable Route Details on Geographical Map drawn to scale with prominent land marks and alignment of cable with reference to road. This shall be prepared on A-3 sheets of 80 GSM.There should be location of joint and important landmark.

b) 	Route Index Diagrams –Profile: These diagrams will contain: -

- Make and size of the cable.

- Offset of cable from centre of the road at every 10 meters;

- Depth profile of Cable at every 10 meter;

- Details of protection with type of protection depicted on it;

- Location of culvert and bridges with their lengths and scheme of laying of HDPE/PLB pipe thereon.

- Important landmarks to facilitated locating the cable in future;

- Location of Joints and pulling manholes.

These diagrams shall be prepared on A-4 sheets of 80 GSM. On one sheet profile of maximum 400 meters shall be given to ensure clarity.

SAFETY PRECAUTIONS: -

6.10.1 Safety Precautions when excavating or working in excavations close to electric cables: -

The Engineer- in-charge of the work should get full information from Electricity undertaking regarding any electric cables, which are known or suspected to exist near the proposed excavation and unless this is done, excavation should not be carried out in the section concerned. The electricity undertaking should be asked to send a representative and work should be preceded with close consultation with them.

Only wooden handled hand tools should be used until the electric cables have been completely exposed. Power Cables, not laid in conduits, are usually protected from above by a cover slab of concrete, brick or stone. They may or may not be protected on the sides. It is safer, therefore, always to drive the point of the pickaxe downwards then uncovering a cable, so that there is less chance of missing such warning slabs. No workman should be permitted to work alone where there are electric cables involved. At least one more man should be working nearby so that help can be given quickly in case of an accident. If disconnection of power could be arranged in that section it will be better. No electric cables shall be moved or altered without the consent of the Electric Authority and they should be contacted to do the needful. If an electric cable is damaged even slightly, it should be reported to the Electric Authority and any warning bricks disturbed during excavation should be replaced while back filling the trench. Before driving a spike into the ground, the presence of other underground properties should be checked. Information on plans regarding the location of power cables need not to be assumed as wholly accurate. Full precautions should be taken in the vicinity until the power cable is uncovered. All electric cables should be regarded as being live and consequently dangerous. Any power is generally dangerous, even low voltage proving fatal in several cases.

6.10.1.1 Electric shock-Action and treatment: - Free the victim from the contact as quickly as possible. He should be jerked away from the live conductors by dry timber, dry rope or dry clothing. Care should be taken not to touch with bare hands as his body may be energized while in contact. Artificial respiration should begin immediately to restore breathing even if life appears to be extinct. Every moment of delay is serious, so, in the meanwhile, a doctor should be called for.

6.10.2 Safety Precautions while working in Public Street and along railway lines:

Where a road or footpath is to be opened up in the course of work, special care should be taken to see that proper protection is provided to prevent any accidents from occurring. Excavation work should be done in such a manner that it will not unduly cause inconvenience to pedestrians or occupants of buildings or obstruct road traffic. Suitable bridges over open trenches should be so planned that these are required for the minimum possible time. Where bridges are constructed to accommodate vehicular traffic and is done near or on railway property, it should be with the full consent and knowledge of the competent railway authorities.

6.9.2.1 Danger from falling material: Care should be taken to see that apparatus, tools or other excavating implements or excavated materials are not left in a dangerous or insecure position so as to fall or be knocked into the trench thereby injuring any workman who may be working inside the trench.

6.9.2.2 Care when working in Excavations: Jumping into a trench is dangerous. If it is deep, workmen should be encouraged to lower themselves. Workers should work at safe distance so as to avoid striking each other accidentally with tools. If the walls of the trench contain glass bits, corroded wire or sharp objects they should be removed carefully. If an obstruction is encountered, it should be carefully uncovered and protected if necessary. If an obstruction is encountered, it should be carefully uncovered and protected if necessary. Care must be taken to see that excavated material is not left in such a position that it is likely to cause any accident or obstruction to a roadway or waterway. If possible the excavated material should be put between the workmen and the traffic without encroaching too much on the road.

6.9.2.3 Danger of cave in: When working in deep trenches in loose soil, timbering up/shoring the sides will prevent soil subsidence. The excavated material should be kept at sufficient distance from the edge of the trench or pit. Vehicles or heavy equipment must not be permitted to approach too close to the excavation. When making tunneled opening, it should be ensured that the soil is compact enough to prevent cave in even under adverse conditions of traffic. Extra care should be taken while excavating near the foundations of buildings or retaining walls. In such cases, excavation should be done gradually and as far as possible in the presence of the owners of the property.

6.10.2.4 Protection of Excavations: Excavations in populated areas, which are not likely to be filled up on the same day should be protected by barriers or other effective means of preventing accidents and the location of all such openings must in any event be indicated by red flags or other suitable warning signs. During the hours from dusk to dawn, adequate number of red warning lamps should be displayed. Supervisory officers should ensure that all excavations are adequately protected in this manner as serious risk and responsibility is involved. Notwithstanding adoption of the above mentioned precautions, works involving excavations should be so arranged as to keep the extent of opened ground and the time to open it to a minimum.

6.10.2.5 Precautions while working on roads: The period between half an hour after sun-set and half an hour before sunrise, and any period of fog or abnormal darkness may also be considered as night for the purpose of these instructions, for the purpose of providing the warning signs. Excavation liable to cause danger to vehicles or the public must at all times be protected with fencing of rope tied to strong uprights or bamboo poles at a suitable height or by some other effective means. Any such temporary erection which is likely to cause obstructions and which is not readily visible should be marked by posts carrying red flags or boards with a red background by day and by continuously lighted lamps at night. The flags and the lamps should be placed in conspicuous positions so as to indicate the pedestrians and drivers of vehicles the full expanse i.e. both width and length of the obstruction. The distance between lamps or between floors should not generally exceed 1.25 m along the width and 6m along length of the obstruction in non congested areas, but 4 meters along the length in congested areas. If the excavation is extensive, sufficient notice to give adequate warning of the danger should be displayed consciously not less than 1.25 m above the ground and close to the excavation. Where any excavation is not clearly visible for a distance of 25m to traffic approaching from any direction or any part of the carriage way of the road in which the excavation exists, a warning notice should be placed on the kerb or edge of all such roads from which the excavation or as near the distance as is practicable but not less than 10 m from the junction of an entering or intersecting road in which the excavation exists. All warnings, in these should have a red background and should be clearly visible and legible. All warning lamps should exhibit a red light, but white lights may be used in addition to facilitate working at night. Wherever required a passage for pedestrians with footbridge should be provided. At excavations, cable drums, tools and all materials likely to offer obstructions should be properly folded round and protected. This applies to jointer‘s tents as well. Leads, hoses etc. stretched and across the carriageway should be guarded adequately for their own protection and also that of the public.

6.10.2.6 Traffic Control: The police authorities are normally responsible for the control of traffic and may require the setting up of traffic controls to reduce the inconvenience occasioned by establishment of a single line of traffic due to restriction in road width or any other form of obstruction caused by the work. As far as possible, such arrangements should be settled in advance. If there are any specific regulations imposed by the local authorities, these should be followed.

6.10.2.7 Work along Railway Lines: Normally all works at Railway crossing is to be done under supervision of the railway authorities concerned, but it is to be borne in mind that use of white, red or green flags by the Departmental staff is positively forbidden to be used when working along a railway line as this practice may cause an accident through engine drivers mistaking them for railway signals. When working along a double line of railway, the men should be warned to keep a sharp look on both the “UP” and “DOWN” lines to avoid the possibility of any accident when trains pass or happen to cross one another near the work spot.

6.10.3 Procedure and Safety Precautions for use of explosives during blasting for trenching: In areas where the cable trench cannot be done manually on account of boulders and rocks, it is necessary to blast the rocks by using suitable explosives. The quality of explosive to be used depends on the nature of the rocks and the kind of boulders. A few types of explosive fuses and detonators normally used for making trenches for cable works are detailed below: a) Gun powder b) Nitrate Mixture c) Gilatine d) Safety fuse e) Electric Detonator f) Ordinary Detonator The permission shall be taken by contractor from local authority for use and at his risk and responsibility.

6.10.3.1 Procedure: A detailed survey of the route is to be done to assess the length of the section where trenching is to be done with the help of blasting. A route diagram of the rocky section may be prepared indicating the length of the route where the explosives are to be used. For the purpose of obtaining license, a longer length of route should be given in the application as in many cases, after digging, rocks appear which was not initially anticipated. Next a license will have to be obtained for use and storing of explosive in that section. If the area falls under a police commissioner, the authority for granting such license is the police commissioner of the concerned area. When the route does not fall in the jurisdiction of a police commissioner, the authority for issuing license is the District Magistrate. The concerned authority should be applied in prescribed form with a route map. The concerned authority will make an enquiry and issue license for using/storing explosives for cables trenching work. Such license will be valid for 15 days only. The license should be got renewed if the blasting operation needs to be extended. Once the license is granted, it is the responsibility of the holders of the license for the proper use of explosives, its transportation and storing.

6.10.3.2 Method of using: The safest explosive is the Gilatine and electric detonator. Gilatine is in the form of a stick. Electric detonator is a type of fuse used for firing the explosive electrically. Holes are made at suitable intervals on rocky terrain or boulders either by air compressor or by manual chipping. The depth of the holes should be 2 to 3 ft. Fill up the holes with small quantity of sand for about 6‖. First the electric detonator is to be inserted into the Gilatine and the Gilatine is to be inserted into the holes keeping the + ve and- ve wirings of electric detonators outside the holes. Again refill the holes with sand. These +ve and-ve insulated wires of detonator are than extended and finally connected to an EXPLODER kept at a distance of not less than 100 m. Now the explosive is ready for blasting. But, before connecting wires to exploder for blasting, all necessary precautions for stopping the traffic, use of red flags, exchange of caution signals, etc. , should be completed and only then Exploder should be connected and operated.

6.10.3.3 Operation of exploder (IDL schaffler type 350 type exploder ) : The type 350 blasting machine consists of a bearing block with blasting machine system and the explosion proof light- alloy injection molded housing. The exploder is held with the left hand. The twist handle is applied to the drive pin, clapped with the right hand turned in the clock wise direction in continuous measurements at the highest speed from the initial position until it reached to a stop. At this stage an indication lamp will glow. When the indication lamp glows, “press button switch” should be pressed. This will extend the electric current to detonator and Gilatine will be detonated. The rock will be blasted out of the trench. Number of holes can be blasted in a single stroke by connecting all such detonators in series connection and finally to the exploder. After blasting, again mazdoors are engaged on the work to clear the debris. It the result of the first blasting is not satisfactory, it should be repeated again on the same place.

6.10.3.3.1 Warning: There may be two reasons for unsatisfactory results of the blasting:

a) Misfire of Gilatine due to leakage of current from detonator.

b) Over loading because of overburdens.

Never pull the broken wire pieces form the holes in such cases. Attempt should not be made to re blast the misfired Gilatine. The safest way is to make a fresh hole by its side and put fresh Gilatine in that hole and blast it.

6.10.3.8 Precaution against stray currents: Where electrically operated equipments is used in locations having conductive ground or continuous metal objects, tests shall be made for stray current to ensure that electrical firing can proceed safely.

TABLE – I

SUMMARY OF TYPE OF PROTECTION REQUIRED FOR LAYING PRACTICE FOR OPTICAL FIBRE CABLE

| S.No. | Depth (In Centimeters) | Type of Protection required |
| --- | --- | --- |
| 1. | 50cms to 89cms | Reinforced concrete casing 4" |
| 2. | 90cms to 119cms | DWC / RCC |
| 3. | 120cms to 165cms | No Protection is required |

*	The relaxation in laying of OFC for depth from 90cms to 164cms shall be granted

by DGM Solan on recommendation of DET concerned.

**	The relaxation in laying of OFC for depth below 90cms to 50 cms shall be granted by CGMT HP Telecom Circle Shimla on recommendation of GMTD Solan.

*** 	The depth below 50cms is not permissible.

****	SDE Incharge of the work must ensure that proper prior intimation is given to the competent authority for less depth relaxation during the execution of work so that the site may be visited in time..

| S. No. | On culvert/bridges/Rail /Road crossing. |
| --- | --- |
| 1. | Nallah dry for nine months in a year. | 1.5M below the bed of Nallah. | PLB pipe in side RCC pipe | As per detail in Fig 4(a). |
| 2. | On culvert / bridges /over other Nallahs. | No particular depth specified. | Various options are available as depicted in Fig.4 (a) to 4(g) | The laying is done as per direction of Engineer in-charge. |
| 3. | Rail bridge /crossing | 1.5M | PLB pipe in side cast iron pipe | As per detail in Fig 3(b). |
| 4. | On road crossing | 1.5M | PLB pipe inside RCC pipe /GI pipe | The laying is done as per direction of Engineer in-charge. |

SECTION – X

AGREEMENT

The successful Tenderer shall have to execute the following agreement:

This agreement made on this________day of ___________ (month)                	   (year)

between M/s________________________________________________________________

___________________________________________________________________________               herein after called “The Contractor”(Which expression shall unless excluded by or repugnant to the context, include its successors, heir, executors, administrative representative and assignee) of the one part & the General Manager Telecom District Solan on behalf of  CHAIRMAN CUM MANAGING DIRECTOR BSNL here in after referred to as the government, of other part.

Where as the contractor has offered to enter into contract with the said Government for the execution of work of trenching & pipe laying OF cable pulling, OF cable splicing and termination, preparation of joint chambers, fixing, painting and sign writing of route/joint indicators and other associated works along- ____________________ route and Section-_____________________ in Solan SSA approved in r/o NIT NO: - GMTD/SOL/Tender/OFC/2012-13/02 Dated 1-06-2012 on the terms and conditions herein contained and the rates approved by the Government (copy of Rates annexed) have been   duly   accepted   and   where as the necessary Security Deposits (_______________________

_________________________________________________________________________) have been furnished in accordance with the provisions of the Tender document and whereas no interest will be claimed on the security deposits. Now these presents witness and it is hereby agreed and declared by and between the parties to these presents as follows.

1)	The contractor shall, during the period of this contact that is to say from…………  to ……………………… or completion of work for Rs				 (In words)					 whichever is earlier or until this contact shall be determined by such notice as is hereinafter mentioned, safely carryout, by means of labours employed at his own expenses and by means of tools, implements and equipment etc, to be supplied by him to his labour at his own expenses, all trenching, pipe laying, cable pulling, cable splicing, joint chamber preparation, fixing, painting and sign writing of route indicators and other associated work as described in Tender documents (annexed to the agreement ), when the government or GMTD Solan or any other persons authorized by GMTD Solan in that behalf require.  It is understood by the contractor that the quantity of work mentioned on the schedule is likely to change as per actual requirements as demanded by exigencies of services.

2)	the NIT (notice inviting Tender), Bid documents (Qualifying and Financial), letter of intent, approved rates, annexed hereto and such other additional particulars, instructions, drawings, work orders as may be found requisite to be given during execution of the work shall be deemed and taken to be an integral part of the contract and shall also be deemed to be included in the expression “The agreement “or” The Contract” wherever herein used.

3)	The contractor shall also supply the requisite number of workmen with means & materials as well as tools, appliances, machines, implements, vehicles for transportation, cartage etc. required for the proper execution of work within the time prescribed in the work orders.

4)	The contractor hereby declares that nobody connected with or in the employment of the Department of Telecommunications/BSNL is not /shall not ever be admitted as partner in the contract.

5)	The contractor shall abide by the terms and conditions, rules, guidelines, construction practices, safety precautions etc. stipulated in the Tender document including any correspondence between the contractor and the Government having bearing on execution of work and payment of work to be done under the contract.

In witness whereof the party presents have here into set their respective hands and seals the day and year in

Above written:

Signed sealed & Delivered by

the above named contactor in

the presence of .

Witness   :

1.

2.

Signed & Delivered on behalf

of the BSNL by the

Witness   :

1.

2

SECTION - XI

LETTER OF AUTHORISATION FOR ATTENDING BID OPENING

Tender number_____________________________________________________________

Subject:  Authorization for attending bid opening on __________________ (date) in ___________ the Tender of ___________________________________________ following person are hereby authorized to attend the bid opening for the Tender mentioned above of behalf of _____________

____________________________________________ (Bidder) in order of preference given below.

Name 		                            		             	Specimen Signatures

Alternate

Representative

Signature of bidder

or

Officer authorized to sign the bid

documents on behalf of the bidder.

1.	Maximum of two representatives will be permitted to attend bid opening. In cases where it is restricted to one, first preference will be allowed. Alternate representative will be   permitted when regular representatives are not able to attend.

2.	Permission for entry to the hall where bids are opened may be refused in case authorization as prescribed above is not recovered.

SECTION - XII

LIST OF THE DOCUMENTS TO BE SUBMITTED ALONG WITH QUALIFYING BID

The Tenderer will have to submit the following documents /deposits with the Technical Bid. Any bid not accompanying with the below mentioned documents /deposits will be liable to be rejected;

i.)	Bid security in accordance to clause no. 8

ii) 	Tender document, in original, (Page 1 to page 143) duly filled in and signed by Tenderer or his authorized representative along with seal on each page. All corrections and overwriting must be initialed with date by the Tenderer or his authorized representative.

iii)	The copy (duly attested by a Gazetted officer) of experience certificate issued by an officer not of the rank below Divisional Engineer.

iv) 	The registration of the firm authenticated copy of partnership deed in cases of partnership firm.

v)	Bid Form, duly filled in, as per section II.

vi)       	Tenderer’s profile duly filled in, as per section III of the Tender document.

vii)   	Original “Power of Attorney” in case person other than the Tenderer has signed the Tender documents.

viii)   	List of qualified experienced personnel, having detail as name and address, who are working for the Tenderer, who will be deployed for the work.

ix)	PAN Number attested copy.

x)	EPF Registration.

xi)        Copy of the Service Tax Registration number.

SECTION – XIII

Rates of Empty Cable Drums

These are the rates of empty cable drums which have to be deducted from the contractor bills as per the Tender document

| Sr. No. | Size of Drum | Rate of Disposal |
| --- | --- | --- |
| 1 | Optical Fibre Cable Drum | 300/- |

Note: - These are fixed rates and no variation shall be acceptable from these rates.

SECTION – XIV

APPENDIX

APPENDIX   'A'

LABOUR BOARD

1.   Name of Work	:

2.   Name of Contractor	:

3.  Address of Contractor	:

4.  Name and address of Telecom Division	:

5.  Name of Telecom Labour Officer	:

6.  Address of Telecom Labour Officer	:

7.  Name of Labour Enforcement Officer	:

8.  Address of Labour Enforcement Officer	:

Date:	 _________________________________________________________________________

Weekly holiday	:

Wages period	:

APENDIX 'B'

FORM XIII

(See Rule 75)

Register of Workmen Employed by Contractor

1) Name and Address of Contractor           :

2) Name and Address of Establishment in

order which contract is carried on           :

3) Name and address of Principal Employer: _________________________________________

_________________________________________________________.

APPENDIX 'C'

FORM XVI

(See Rule 78 (2) (A)

MUSTER ROLL

1.  Name and Address of Contractor        	  :

2.  Name and Address of Establishment in

order which contract is carried on                            :

3.  Nature and location of work                    	:

4.  Name and address of Principal Employer:  ____________________________________________

__________________________________________.

APPENDIX 'D'

FORM XVII

(See Rule 78 (2) (a)

REGISTER OF WAGES

1.  Name and Address of Contractor           :

2.  Name and Address of Establishment in

order which contract is carried on           :

3.  Nature and location of work                    :

4.  Name and address of Principal Employer:

5.  Wages period Monthly/Fortnightly          :

APPENDIX 'E'

Wage Card No....

Wage Card

1.  Name and Address of Contractor        :

2.  Name of work with location                :

3.  Name of workmen                                :

4.  Rate of wages                                        :

5.  Date of issue                                          :

6.  Designation                                           :

Month/Fortnight

_________________________________________________________________________________

1  2  3   4   5   6  7  8   9    10   11  12  13   14   15  16  17  18  19  20  21  22  23  24  25  26 27 28 29 30 31

_________________________________________________________________________________

Morning                                                                                                                       Rate

Evening                                                                                                                       Amount

Initial

Received from ..................the Sum of Rs...................on account of my wages

The Wages Card is valid for one month from the date of issue.

APPENDIX ‘F’

Form XIV

(See Rule 76)

EMPLOYMENT CARD

1.  Name and Address of Contractor                   :

2.  Name and address of Establishment

in under which contract Ls carried on             :

3.  Name of work and location of work                :

4.  Name and address of Principal Employer        :

5.  Name of the workman                                      :

6.  Sl. No. in the register of workman employed   :

7.  Nature of employment designation                   :

8.  Wage rate (with particulars of unit in

case of piece WORK)                                        :

9.  Wage period                                                       :

10. Tenure of employment Remarks                       :

11. Remarks                                                             :

Signature of Contractor

APPENDIX  'G'

FORM XV

(See Rule 77)

SERVICE CERTIFICATE

1.  Name and Address of Contractor                          :

2.  Name and address of Establishment

in under which contract is carried on                     :

3.  Name and location of work                                    :

4.  Name and address of Principal Employer               :

5.  Name and address of the workman                          :

6.  Age or date of birth                                                  :

7.  Identification Marks                                                 :

8.  Father's/Husband's name                                           :

APPENDIX ‘H’

FORM XII

(See Rule 78 (2) (d)

REGISTER OF FINES

1.  Name and Address of Contractor                       :

2.  Name and address of Establishment

in under which contract is carried on                  :

3.  Name of work and location of work                    :

4.  Name and address of Principal Employer            :

APPENDIX  '1'

FORM  XIX

(See Rule 78 (2) (b)

WAGES SLIP

Name and Address of contractor                                :

Name and Father's/Husband’s name

of workman                                                                 :

Nature and location of work                                        :

For the Week/Fortnight/Month ending                        :

1.  No of days worked                                                  :

2.  No. of units worked in case of piece                       :

3.  Rate of daily wages/piece rate                                 :

4.  Amount of overtime wages                                      :

5.  Gross wages payable                                                :

6.  Deductions, if any                                                    :

7.  Net amount of wages paid                                        :

Initials of the Contractor

or

His Representative

BHARAT SANCHAR NIGAM LIMITED

O/o GENERAL MANAGER TELECOM DISTRICT

SOLAN (HP)

BID DOCUMENT

(FINANCIAL)

Tender No: - GMTD/SOL/Tender/OFC/2014-15/07.     Dated :- 04-02-2015.

Route Name: -

Section: -

SECTION – XV

(FINANCIAL BID)

## Schedule of Rates for OFC construction work in SOLAN SSA

| S. No | Description of work | Unit of Measurement | Rates Per unit ( In Rupees) |
| --- | --- | --- | --- |
| 1.1 | Excavating trenches of dimensions (Width 0.45 m top and 0.30 bottom) up to a depth of 165 cm, dressing sides, bed leveling and dewatering of rain water and back filling the excavated trenches after laying the HDPE pipe with or without protection including diversion for traffic, night signals, fixing of caution boards, watching, fencing, cutting trees and bushes etc. and sundries lump sum . | - | - |
|  | A. Non-Rocky soil ( SOFT SOIL) | Per Mtr | 60.00 |
|  | B. Rocky-soft soil( Soft soil mixed with boulders,concrete and/ or bitumen) ( SOFT ROCK) | Per Mtr | 170.00 |
|  | C. Rocy-hard soil ( HARD ROCK) | Per Mtr | 380.00 |
| 1.2 | Trenchless digging with HDD machine to lay PLB pipes,including PLB pipe laying(HDD machine having a capacity more than 10 Tonn Pull-back and should be able to bore upto 200 meters in a single stretch)as per construction specification of the tender to a depth of 1.65 Mtrs in bitumanised/concret set stone and avoiding any damage to the existing under ground cables/public property (BSNL will supply HDPE pipes or coils, HDPE sockets & end caps only.All other material and equipment/tools required for executing the said work are to be supplied by the contractor) | - | - |
|  | A. Laying of PLB pipe /coils (single pipe) | Per Mtr | 150.00 |
|  | B. Laying of PLB pipe /coils (02-03 pipes) | Per Mtr | 175.00 |
|  | C. Laying of PLB pipe /coils (04-07 pipes) | Per Mtr | 200.00 |
| 2 | Laying of HDPE pipes/coils with leveling alongwith fixing with HDPE sockets /HDPE couplers and laying of 40/33mm PLB in GI pipe /DWC pipe including carriage from stores | Per Mtr | 5.00 |
| 3 | Laying of PLB Pipe/GI pipe duct through horizontal mannual boring method for Road/Rail crossing including transportation of GI pipe for laying of 40 mm PLB pipe. (The GI Pipe of 65mm dia will be supplied by BSNL) | Per Mtr | 110.00 |
| 4.1 | Laying with levelling and fixing of GI pipe/DWC of 65 mm outer diameter through clamps on the wheel guard of the bridge and laying 40mm PLB inside GI /DWC pipes including transportation for laying of 40 mm PLB pipe. (The GI Pipe/DWC pipes of 65mm dia & 40mm PLB will be supplied by BSNL) . All other material and equipment /tools required for executing the said work are to be supplied by the contractor. | Per Mtr | 16.50 |
| 4.2 | Laying with levelling and fixing of Full DWC round pipe out side and below parapet wall of the bridge duly fixed by clamps at 1 meter interval and transportation for laying of 40 mm PLB pipe for the bridges more than 100 Meters. BSNL will supply DWC pipes. All other material and equipment/tools required for executing the said work shall be supplied by the contractor. | Per meter | 70.00 |
| 4.3 | Supply of Clamps per KG (with gauze 5mm) As per instructions of field DET | Per Kg | 60.00 |
| 5.1 | Laying with levelling and fixing of GI Pipes of 65 mm outer diameter in the trench including transportation for laying of 40 mm PLB pipe. (The GI Pipe of 65mm dia & 40mm PLB will be supplied by BSNL) | Per Mtr | 16.00 |
| 5.2 | Laying with levelling and fixing of Full Round DWC/ Full round RCC pipe including transportation for laying of 40 mm PLB pipe. (The Full round DWC Pipe/RCC/PLB Pipe 40mm PLB will be supplied by BSNL) | Per Mtr | 8.00 |
| 5.3 | Laying with levelling and fixing of half Round (Split ) DWC pipe/ Split RCC Pipe including transportation. (The half round (split) DWC Pipe/RCC of 90mm dia will be supplied by BSNL) | Per Mtr | 6.00 |
| 5.4 | Providing CC of size 25 Cms X 25 Cms for enclosing G.I./ PLB pipe of diameter upto 65 mm with CC of ratio 1:2:4 including transportation supply of all material for CC work by the contractor in presence of site incharge.(The GI Pipe of 65mm dia & 40mm PLB will be supplied by BSNL) | Per Mtr | 160/m or 2700 per Cubic M |
| 5.5 | Laying of 65 mm GI Pipe and Providing RCC of size 25 Cms X 25 Cms for enclosing GI pipes of diameter 65 mm with CC of ratio 1:2:4 with 4 nos of 6 mm dia iron rods with rings at interval of 0.5 M of 6 mm dia iron rods for fixing including supply of all material in presence of site incharge (The GI Pipe of 65mm dia & 40mm PLB will be supplied by BSNL) | Per Mtr | 200/m or 3380 per Cubic M |
| 6.1 | Opening of Brick Chamber, Blowing 24F O.F.Cable, Sealing of HDPE/PLB Pipes by Rubber Bushes in Brick Chamber, providing HDPE/RCC/DWC Split Pipes in the chambers & Back Filling it. BSNL will supply OF cable, rubber bush, split RCC/HDPE pipes. All other materials and equipment required for executing the said work shall be arranged by the contractor. | Per Mtr | 8.00 |
| 6.2 | Opening of Manhole of Existing Civil duct/ OAN ducts ,De-watering of Manholes, Repairing & clearing of Existing Civil duct, Pulling O.F.Cable, Sealing of HDPE/PLB Pipes by Rubber Bushes in Manholes, providing HDPE in the chambers & closing of Manholes etc. BSNL will supply OF cable, rubber bush, split RCC/HDPE pipes. All other materials and equipment required for executing the said work shall be arranged by the contractor. | Per Mtr | 14.00 |
| 7.1 | Digging of pit for jointing chamber and a)Supply & Fixing of Pre -cast RCC chamber with CC ratio 1:2:4, complete with base plate, filling of RCC chamber with clean sand, placing of Pre-cast RCC slabs on RCC chamber (as per Figure 7 Section VIII of tender document) and back filling the pit with fine sand including transportation of Pre-cast RCC chamber.from divisional store to work site. | Per chamber | 4000 for supply & fixing, 1200 for fixing only |
| 7.2 | b) Digging of pit and Making of Bricks Joint Chamber having internal dimensions of 1.2 m x 1.2 m x1 m (H) having wall thickness of 9” using cement mortar mix of 1:5 (1: cement, 5: fine sand).to be constructed on the base of size 1.7 m x 1.7 m x 0.15 m (thickness).with cover & back filling the pit with fine sand as per construction specification of Clause 7.1 of Section VIII including cost of material & transportation.. | Per chamber | 4800 |
| 8 | Splicing of all the fibers of OF cable laid at every joint and making termination at the ends. | - | - |
|  | a) 24/48 fibers | Per Joint/ Termination | 3000.00 |
|  | b) 96 fibers | Per Joint/ Termination | 5000.00 |
|  | c) 288 fibers | Per Joint/ Termination | 6000.00 |
| 9 | A. Digging of pit 1 meter towards jungle side on each manhole/joint/route chamber for fixing of route/joint indicator, tranportation from stores to locations, a)Supply & Fixing of Route Indicators including transportation concreting,painting and sign writing with paint( as per specifications Fig.6 under Section VIII of the Tender Document ) B) Fixing with concreting of Route Indicators, painting & Signwriting with paint( as per specifications Fig.6 under Section VIII of the Tender Document )to be done by Contractor,including transportation .BSNL will supply the route indicators. | Per Indicator | a)425 for supply & fixing b)150 for fixing only |
| 10 | Supply of route index diagram in 3 Nos of hard colour copies as well as Two soft copy on CD. | Per set of three copies | 200 per KM |
| 11 | Digging of pit for Manhole chamber and making of RCC Manhole chamber complete With cover & backfilling the pit as per specifications mentioned in the tender document. (As per specification in BSNL) | Per manhole | 42000.00 |
| 12 | Supply & fixing of FRP Manhole as per specifications mentioned in the tender document. The Contractor shall arrange all materials and equipment required for work (As per specification in BSNL) | Per Manhole | 30000.00 |
| 13 | Cost of recovery empty cable drums of size 24/48/96/288 fibers | Per drum | 300.00 |

- Non rocky* = This will include all types of soils - soft soil/hard soil/murrum i.e. any strata, such as sand, gravel, loam, day, mud, black cotton murrum, shingle, river or nallah bed boulders, soling of roads, paths etc. and hard core, macadam surface of any description (water bound grouted tarmac etc.), lime concrete, mud concrete and their mixtures for excavation of which need application of picks, showels, sacrifiers, ripper and other manual  digging implements.

2.   Soft rock# =Any rock which can be excavated  by splitting with crow bars or picks and does not  require blasting, wedging or similar means such as lime stone, sand stone, hard laterite, hard conglomerate.  The un-reinforced cement concrete roads as well as other type of roads (except RCC) are also included under this category.

3.    Hard rock@ =Any rock or boulder for the excavation of which blasting is required such as quartzite, granite, basalt reinforced cement concrete and the like.

##### Section XVI

Financial Bid

To,

The SSA Head

BSNL, Solan.

# Sub.: Our Financial Bid for –  “Tender For Optical Fibre Cable Construction Works in SOLAN SSA”

# Ref.: 	__________________________________________________________________.

Dear sir,

Having examined the tender documents, terms and conditions stipulated therein, specifications of work etc., we the under signed offer execute the OF Cable Construction work in conformity with the said specifications and conditions of contract at the percentage (Below/at per/above) an standard schedule rates quoted as under: -

In figures ………………………….……%

In words ……………………………….. Percent .

# OR

In words ……………………………….. .

# OR

In figures …………………%

In words ……………………………….. Percent .

If our Bid is accepted, we shall submit the securities as per the conditions mentioned in the contract.

I/We agree to abide by this Bid for a period of 240 days from the date of opening of financial bid and it shall remain binding upon us and may be accepted at any time before the expiry of that period.

Date : __________								Signature of Bidder

______________________

______________________

(Name & Address)

Note: - 	(i)          The bidder has to quote the rates without Service Tax.

(ii)         Service Tax will be paid by the BSNL on production of proof of deposition of Service Tax

SECTION - XVII

CERTIFICATE BY BIDDER IN CASE OF DOWNLOAD

If the Tender is downloaded from website and this certificate is not signed by the bidder, the Tender will be rejected

It is certified that the Bid Document in r/o Tender for Optical Fiber Construction work  in the jurisdiction of Solan SSA, downloaded from website www.hp.bsnl.co.in  has not been edited by me / us and it is the reproduce of one that was loaded on the web site.

Signature of Bidder with seal

# Text boxes

Passport size photograph of the bidder/authorized signatory holding power of Attorney

BELOW

#### B

AT  PAR

ABOVE

#### ABOVE